KADJEBI DISTRICT ASSEMBLY

2021 COMPOSITE ANNUAL ACTION PLAN

PREPARED BY: DPCU, SEPTEMBER 2021

TABLE OF CONTENT

KADJEBI DISTRICT ASSEMBLY	1

ANNUAL ACTION PLAN FOR 2021	1

1.0 INTRODUCTION	1

Objectives of the plan	2

Methodology and Approach	3

FUNDING SOURCES OF THE PLAN	3

COMPOSITE ANNUAL ACTION PLAN	5

# KADJEBI DISTRICT ASSEMBLY

# ANNUAL ACTION PLAN FOR 2021

- INTRODUCTION

1.1 BACKGROUND OF THE DISTRICT

Kadjebi District was created as an Assembly by Legislative Instrument (L.I.) 1465 in 1989 and forms part of the 8 Municipal and District Assemblies of the Oti Region of Ghana

The District is located South of the Oti Region of Ghana and forms part of the Eight (8) districts of the Region.  It is bordered to the north by Nkwanta South Municipal, to the south by the Jasikan District, to the North West by Krachi East to the south east by Biakoye District. Kadjebi district has a long boarder eastwards with the by the Republic of Togo and has a total land area of 949 km2.  The strategic location of the district promotes cross border activities with the republic of Togo

The district has an average height of about 180 meters above sea level rising to about 600 meters towards the Ghana – Togo Border.  The district is blessed with beautiful landscape of hills, mountains and valleys.  The land form however is not a hindrance to road construction in the district.

The climate in the district is characterized by average monthly temperature of about 25oC and rainfall is between 1400 mm and 1800mm. Rainfall is generally heavy and starts from March and ends between October and November each year.  The peak of rainfall occurs in June.  These conditions are conducive for agriculture production. One major climatic problem, facing the district is severe rainstorms, which destroy farm crops, buildings and also cause severe soil erosion in some places especially during the rains.  Also, the prolonged drought during the dry season (December–March) is a major source of worry to farmers who are engaged in dry season agriculture production especially vegetables.

The Kadjebi district especially in the rainy season is generally green with trees covering beautiful landscape of mountains, hills and valleys. 90% of the district is predominantly covered with secondary rain forest.  The forests have economic trees such as wawa, mahogany, odum, red wood, raffia palm and bamboo grooves to support the wood processing industry.  Animal and bird species such as antelopes, monkeys, glasscutters,

weaverbirds and parrots abound in the forest.  The forest reserve with its animal and bird species is potential for eco-tourism development in the district.Activities such as hunting of animals, palm wine tapping and the method used in land clearing for farming cause bush fires which degrade the environment. Bush fire prone areas in the district include Todome, Dika, Ampeyo, Koru, Pampawie, Dapaa, Olobobi, Pepesu, Bekpo, Dodo-Bethel, Kadjebi, Dodo-Amanfrom and Dodo-Tamale.  The Ghana National Fire Service established at Kadjebi has a staff of twelve (12) personnel. Twenty-five (25) Fire Volunteers squads in the district have become dormant because they are not equipped and motivated to fight bush fires in the district.  The brand new Fire tender provided by government in 2012 is very effective in fighting in within the district and even beyond.

The total population of Kadjebi District is 59,303.  This is made up of 29,951 (51%) males and 29,303 (48.6%) females.

The Kadjebi District provides only 2.80% of the total Volta Region population for 2010.  The population growth rate of the district stands at 4.9%.  This is considered too high compared with the growth rates of 1.9% and 2.7% for the Region and the nation respectively.

The Kadjebi district assembly’s 2014-2017 medium term plan was prepared in line with the GSGDA II and it main focus is to address the economic imbalances and to build a robots economy with the possibility of sustaining and accelerated growth and poverty reduction towards archiving the Millennium Development Goals and middle income status. The objective of the Assembly is to implement policies and programmes outlined in the plan. And also effectively monitor implementation to archive expected output and outcomes which can inform future plans.

# Objectives of the plan

The main purpose of the formulating annual action plan is to identify the sub project interventions for implementation in 2017. The plan was formed in line with GSGDA II thematic area as follows:

- Ensuring and sustaining macroeconomic stability

- Enhancing competitiveness of Ghana private sector

- Accelerated agricultural modernization and sustainable natural resource management

- Infrastructure and human settlement development

- Human development ,productivity and employment

- Transparent and accountable governance

# Methodology and Approach

In preparing the annual work plan, these procedures were followed:

- A stakeholder’s workshop involving members of the expanded DPCU, traditional authorities, town/area councils and opinion leaders was held for the identification of sub-projects under various sources of funding. After discussions, brainstorming, and plenary sessions, sub projects were selected in accordance with the objectives and development needs of the people identified in the MTDP.

- There was also DPCU meeting to synthesize and finalize the document.

# FUNDING SOURCES OF THE PLAN

District assembly common fund (DACF)    1,075,722.00

District development facility (DDF)        484,836.00

Internal generated fund (IGF)             340,986.52

Development partners (DP)               5,000.00

PWD                                 62,769.84

MPs Common Fund                     200,000.00

The estimates are however provisional and indicative, therefore they do not necessarily represent the actual cost of sub projects until the designs have been prepared for implementation.

Monitoring and evaluation

The District Planning Coordinating Units (DPCU) in cooperation with the DWD will be responsible for gathering data at the project sites by routine site visit and preparing and submitting quarterly report to VRCC in accordance with NDPC guidelines. Beneficiary community, institutions and other relevant staffs will be drawn into the monitoring team where appropriate. Data gathered at the district and zonal level will be disseminated and discussed at the learning and evaluation platforms to be established at the district and zonal level.

# 2021 COMPOSITE ANNUAL ACTION PLAN

| Sub-programmes | Activities (Operations) |  | Location | Baseline | Output Indicators | Quarterly Time schedule |  |  |  |  | Indicative Budget |  |  |  | Implementing Agencies |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 1st | 2nd |  | 3rd | 4th | GoG |  | IGF | DONOR | Lead |  |  |  |  | collaborating |  |  |
| Goal 4. GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme 1: Management and Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Central Administration | - Involve TAs in decision making processes of the Assembly |  | Kadjebi | √ | TAs involved decision making processes of the Assembly | √ | √ |  | √ | √ | 6,000.00 |  |  |  | KADA |  |  |  |  | HR |  |  |
|  | - Embark on participatory M&E activities on development projects |  | District Wide | √ | Improved engagement of CSOs in public policy making | √ | √ |  | √ | √ | 50,000.00 |  |  |  | DPCU |  |  |  |  | Relevant stakeholders |  |  |
|  | - Implement the popular participation strategy of the Assembly |  | District Wide | √ | Popular participation strategy of the Assembly implemented | √ | √ |  | √ | √ | 9,000.00 |  |  |  | KADA |  |  |  |  | HR/ DPCU |  |  |
|  | - Ensure effective operationalization of the client service unit |  | DA | √ | Effective operationalization of the client service unit ensured | √ | √ |  | √ | √ | 5,000.00 |  |  |  | KADA |  |  |  |  | HR/ DPCU |  |  |
|  | - Celebrate 3No. National and International Anniversaries/ Days and events annually |  | District Wide | 5 | National and International days celebrated | √ | √ |  | √ | √ | 13,000.00 |  |  | 20,000.00 | KADA |  |  |  |  | HR/ DPCU |  |  |
|  | - Procurement of office supplies and consumables, |  | DA/Area Councils | √ | Office supplies and consumables supplied | √ | √ |  | √ | √ | 20,000.00 |  | 10,000.00 |  | KADA |  |  |  |  | PO/ DPCU |  |  |
|  | - Organize 4No. annual Town Hall meetings and other public forums at Area Council levels |  | District | 4 | Town hall meetings organized | √ | √ |  | √ | √ |  |  | 30,000.00 |  | KADA |  |  |  |  | HR/ DPCU |  |  |
|  | - Support other decentralized departments |  | District Wide | √ | Other decentralized departments supported | √ | √ |  | √ | √ |  |  | 50,000.00 |  | KADA |  |  |  |  | DPCU |  |  |
|  | - Logistics for Procurement and Internal Audit management |  | Kadjebi | √ | Enhanced output | √ | √ |  | √ | √ | 50,000 |  |  |  | DPCU |  |  |  |  | KADA |  |  |
|  | - Implementation of legislative enactments and oversight |  | Kadjebi | √ | Improved governance | √ | √ |  | √ | √ | 60,000 |  |  |  | DPCU |  |  |  |  | KADA |  |  |
|  | - Maintenance of Official vehicles |  | Kadjebi | √ | Improved transportation | √ | √ |  | √ | √ | 40,000 |  |  |  | TU |  |  |  |  | KADA |  |  |
|  | - Support the operationalization of KADA’s ICT platforms and internet and Intercom services. |  | Kadjebi | - | Increased access to ICT |  |  |  |  |  | 20,000.00 |  |  |  | KADA |  |  |  |  | DPCU |  |  |
|  | - Support Assembly's meetings/workshops/seminars |  | Kadjebi | √ | Meetings/workshops/seminars held | √ | √ |  | √ | √ | 15,000.00 |  | 20,000.00 |  | KADA |  |  |  |  | HR/ DPCU |  |  |
|  | Internal management of the Assembly |  |  |  |  |  |  |  |  |  |  |  | 200,000.00 |  | KADA |  |  |  |  | DPCU |  |  |
|  | - Provision for Local and International Affiliations and any unplanned activity/Government directive |  | District wide |  |  | √ | √ |  | √ | √ | 150,000.00 |  |  |  | KADA |  |  |  |  | DPCU |  |  |
|  | - Provide office equipment, logistics, furniture & fittings |  | DA/Area councils | √ | Furniture and fittings procured | √ | √ |  | √ | √ | 12,000.00 |  | 20,000.00 |  | KADA |  |  |  |  | HR/ DPCU |  |  |
| Planning, Budgeting and Statistics | - Undertake quarterly monitoring and evaluation of development projects |  | Kadjebi | √ | Monitoring conducted | √ | √ |  | √ | √ | 20,000.00 |  |  |  | KADA |  |  |  |  | DPCU |  |  |
|  | - Mid Year Review of AAP and Composite Budget |  | Kadjebi | √ | Mid-year reviews conducted | √ | √ |  | √ | √ | 30,000.00 |  |  | 20,000.00 | KADA |  |  |  |  | DPCU |  |  |
|  | - Facilitate the preparation of 2022-2025 District medium term development Plan |  | Kadjebi | √ | 2022-2025 MTDP Prepared | √ | √ |  | √ | √ | 50,000.00 |  |  | 30,000.00 | KADA |  |  |  |  | GIZ,DPCU |  |  |
|  | - Facilitate the preparation of 2021 fee fixing, Annual action plan and composite budget |  | Kadjebi | 3 | 2019 fee fixing, Annual action plan and composite budget prepared |  |  |  | √ | √ | 30,000.00 |  |  |  | KADA |  |  |  |  | DPCU, GIZ |  |  |
|  | - Data collection on Depts (Health, Education, Agric etc) |  | District wide | 0 | Data collection undertaken | √ | √ |  | √ | √ | 3000.00 |  |  |  | Planning Unit |  |  |  |  | DPCU |  |  |
|  | - Undertake supervision of the 2021 Housing and population Census |  | District wide | 0 | Supervision of 2021 PHC undertaken | √ | √ |  | √ | √ | 1000.00 |  |  |  | Planning unit |  |  |  |  | DPCU |  |  |
|  | - Procurement of Office Furniture |  | Kadjebi | 0 | Office Furniture Procured | √ | √ |  | √ | √ | 1000.00 |  |  |  | Planning unit |  |  |  |  | KADA |  |  |
|  | - Valuation of all fixed assets |  | Municipal Wide | - | All fixed assets valuated | √ | √ |  | √ | √ | 50,000.00 |  |  |  | KADA |  |  |  |  | Lands Commission |  |  |
| Finance | - Organize 4No. Public sensitization on tax obligation |  | District Wide | 2 | IGF increased by 10% | √ | √ |  | √ | √ |  |  | 10,000.00 |  | Finance Dept. |  |  |  |  | Budget Unit/ F&A Sub-Committee |  |  |
|  | - Organize 12No. monthly supervision of all revenue collections |  | District Wide | 5 | Increased revenue generation | √ | √ |  | √ | √ | 10,000.00 |  |  |  | Finance Dept. |  |  |  |  | Budget Unit/ F&A Sub-Committee |  |  |
|  | - Carry out Revaluation of properties in the District |  | Municipal Wide | - | All properties revaluated | √ | √ |  | √ | √ | 50,000.00 |  |  |  | KADA |  |  |  |  | Lands Commission |  |  |
|  | - Data collection to update business register of the District |  | District Wide | √ | % increase in revenue generation | √ | √ |  | √ | √ | 10,000.00 |  |  |  | Finance Dept. |  |  |  |  | Budget Unit/ F&A Sub-Committee |  |  |
|  | - Facilitate the preparation and implementation of 2021 Revenue Improvement Action Plan (RIAP) |  | District Wide | √ | Revenue performance enhanced | √ | √ |  | √ | √ |  |  | 10,000.00 |  | DPCU |  |  |  |  | Revenue Unit |  |  |
| Human Resource | - Organize training on resource mobilisation with emphasis on IGF |  | District Wide | √ | Enhanced staff performance | √ | √ |  | √ | √ | 20,000.00 |  |  |  | KADA |  |  |  |  | HR/ DPCU |  |  |
|  | - Organize 2No. capacity training programmes for DPCU and assembly members on M&E skills |  | Kadjebi | √ | DPCU and Assembly members trained | √ |  |  |  |  | 10,000.00 |  |  |  | KADA |  |  |  |  | HR/ DPCU,GIZ |  |  |
|  | - Organise training for staff on records management |  | District Wide | √ | Staff trained on records management |  | √ |  |  |  | 10,000.00 |  |  |  | HRD |  |  |  |  | KADA |  |  |
|  | - Organize capacity training programmes on LGS Protocols |  | Kadjebi | √ | Enhanced staff performance | √ |  |  |  |  | 10,000.00 |  |  |  | HRD |  |  |  |  | KADA |  |  |
|  | - Organise training for staff on effective communication and report writing skills |  | Kadjebi |  | Staff trained on effective comm and writing skills |  |  |  |  | √ |  |  |  |  | HRD |  |  |  |  | KADA |  |  |
|  | - Attend workshops, seminars and conferences |  | Kadjebi |  | Enhanced staff capacity | √ | √ |  | √ | √ | 6000.00 |  |  |  | HRD |  |  |  |  | KADA |  |  |
|  | - Preparation and submission of monthly reports |  | Kadjebi |  | Kadjebi Monthly reports prepared and submitted | √ | √ |  | √ | √ | 2000.00 |  |  |  | HR |  |  |  |  | KADA |  |  |
|  | - Monitoring of Field Staff |  |  |  |  | √ | √ |  | √ | √ | 1000.00 |  |  |  | HR |  |  |  |  | KADA |  |  |
|  | Procurement and maintenance of office supplies and equipment |  | Kadjebi |  | Office supplies and equipments procured | √ | √ |  | √ | √ | 2000.00 |  |  |  | HR |  |  |  |  | KADA |  |  |
| GOAL 1: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme 4: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Local Economic Development | - Rehabilitation and fencing of slaughter house |  | Kadjebi | - | Improved meat hygiene and job creation | √ |  |  |  |  |  |  | 140,000.00 |  | KADA |  |  |  |  | EHSU |  |  |
|  | - Rehabilitation of 4No. Market infrastructure |  | , Dodi Papase, Pampawie and Poase cement | - | Increased commercial activities | √ | √ |  | √ | √ | 500,000.00 |  |  |  | KADA |  |  |  |  | Community members |  |  |
|  | - Supply start-up kits to SMEs |  | District Wide | √ | Increased private sector productivity | √ | √ |  | √ | √ | 12,000.00 |  |  |  | BAC |  |  |  |  | DPCU |  |  |
|  | - Facilitate the implementation of the “One District, One Factory programme |  | District Wide | - | Increased job avenues | √ | √ |  | √ | √ | 5,000.00 |  |  |  | KADA |  |  |  |  | BAC |  |  |
|  | - Facilitate the extension of electricity to all parts of the District to promote development of businesses |  | District Wide | √ | Increased access to power for production | √ | √ |  | √ | √ | 80,000.00 |  |  |  | ECG |  |  |  |  | KADA |  |  |
|  | - Partner the private sector to develop, promote and create the tourism potentials in the District |  | District Wide | - | Increased IGF capacity of the Assembly | √ | √ |  | √ | √ | 10,000.00 |  |  |  | KADA |  |  |  |  | community |  |  |
| Agricultural Development | - Organize 4No. training programmes for staff and farmers on rice and maize production |  | District Wide | 2 | Increased agricultural productivity | √ | √ |  | √ | √ | 30,000.00 |  |  |  | Dept. Of Agric |  |  |  |  | KADA |  |  |
|  | - Organize 4No. training programmes for staff and farmers on soil fertility management and fertilizer use |  | District Wide | 2 | Increased agricultural productivity | √ | √ |  | √ | √ | 5000.00 |  |  |  | Dept. Of Agric |  |  |  |  | KADA |  |  |
|  | - Hold stakeholders meeting to review agric activities in the district |  | Kadjebi | 1 | Stakeholder review meeting held |  | √ |  |  |  | 4000.00 |  |  |  | Dept. Of Agric |  |  |  |  | KADA |  |  |
|  | - Organise a 2day training for women farmers and processors on commodity processing, utilisation and packaging in two communities per quarter |  |  |  |  | √ | √ |  | √ | √ | 3000.00 |  |  |  | Dept. Of Agric |  |  |  |  | KADA |  |  |
|  | - Organize 4No. training programmes for staff and farmers on farm planning and budget |  | District Wide | 2 | Increased productivity | √ | √ |  | √ | √ | 10,000.00 |  |  |  | Dept. of Agric |  |  |  |  | KADA |  |  |
|  | - Organize 4No. training programmes for staff and farmers on principle of crops and livestock production |  | District Wide | 2 | Increased crops and livestock production | √ | √ |  | √ | √ | - |  |  |  | Dept. of Agric |  |  |  |  | Vert. Services |  |  |
|  | - Create and develop land banks for agricultural activities |  | District Wide | - | Availability of land for agricultural use | √ | √ |  | √ | √ |  |  |  | 10,000.00 | Dept. of Agric |  |  |  |  | Communities |  |  |
|  | - Facilitate the construction of 2No. irrigation infrastructure |  | Menusu and Dodo Tamale | √ | Increased irrigation farming | √ | √ |  | √ | √ | 30,000.00 |  |  |  | Dept. of Agric |  |  |  |  | Private sector/ GOG |  |  |
|  | - Train farmers and staff on storage of cereals |  | District Wide | √ | Reduced post-harvest loses | √ | √ |  | √ | √ |  |  | 10,000.00 |  | Dept. of Agric |  |  |  |  | Farmers |  |  |
|  | - Develop and Print technical and educational materials (including billboards and stickers) to farmers |  | District Wide | √ | Increased yield | √ | √ |  | √ | √ | 20,000.03000.00 |  |  |  | Dept. of Agric |  |  |  |  | CIDA |  |  |
|  | - Facilitate the supply of fertilizers to farmers |  | District Wide | √ | Increased crop yield | √ | √ |  | √ | √ | 10,000.00 |  |  |  | Dept. of Agric |  |  |  |  | GOG |  |  |
|  | - Intensify the use of radio and information van for knowledge dissemination |  | District Wide | 12 | Increased access to agriculture information | √ | √ |  | √ | √ | 10,000.00 |  |  |  | Dept. of Agric |  |  |  |  | ISD |  |  |
|  | - Embark on field and home visits by Technical Staff |  | District Wide | 13 | Increased access to agriculture information | √ | √ |  | √ | √ | 15,000.00 |  |  |  | Dept. of Agric |  |  |  |  | Assembly members |  |  |
| GOAL 2: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme 2: Social Services Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programmes | Activities (Operations) |  | Location | Baseline | Output Indicators | Quarterly Time schedule |  |  |  |  |  | Indicative Budget |  |  |  | Implementing Agencies |  |  |  |  |  |  |
|  |  |  |  |  |  | 1st | 2nd | 3rd |  | 4th |  | GoG | IGF | DONOR |  | Lead |  | collaborating |  |  |  |  |
| Education, Youth& sports and library service | - Construction 4No. 3 unit classroom blocks office and store |  | Okanta, Ampeyo,KASEC, Ahamansu | 4 | Increased access to education | √ | √ | √ |  | √ |  | 428,000.00 |  |  |  | KADA |  | GetFund |  |  |  |  |
|  | - Construction of 1No. 6 unit classroom blocks |  | Kosamba | 1 | Increased access to education | √ | √ | √ |  | √ |  | 40,000.00 |  |  |  | KADA |  |  |  | GetFund |  |  |
|  | - Construct 1No. 3 unit classrooms blocks, office store, ICT and urinal for Anwar Islamic |  | Dodi Papase | - | Improved educational quality | √ | √ | √ |  | √ |  | 300,000.00 |  |  |  | KADA |  |  |  | GetFund |  |  |
|  | - Support for self-help/counterpart funding projects |  | District Wide | 2 | Increased access to education | √ | √ | √ |  | √ |  | 83,786.10 |  |  |  | KADA |  |  |  | Community/Donor |  |  |
|  | - Support school sports and cultural activities |  | District Wide | 4 | Improved recreation | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | KADA |  |  |  | World Vision |  |  |
|  | - Organize annual my First Day at School programmes |  | District Wide | 1 | Increased access to education | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | KADA |  |  |  | GES |  |  |
|  | - Support annual STMIE clinics |  | District Wide | 30 | Improved capacity | √ | √ | √ |  | √ |  | 12,000.00 |  |  |  | KADA |  |  |  | GES |  |  |
|  | - Provide material support(uniforms/shoes) to needy but brilliant students, especially Girls |  | District Wide | 300 | Increased access to education | √ | √ | √ |  | √ |  | 15,000.00 |  |  |  | MP |  |  |  | KADA |  |  |
|  | - Provide financial support to needy but brilliant students, especially Girls |  | District Wide | 12 | Increased access to education | √ | √ | √ |  | √ |  | 15,000.00 |  |  |  | MP |  |  |  | KADA |  |  |
|  | - Facilitate career guidance in schools |  | District Wide | √ |  | √ | √ | √ |  | √ |  |  | 5,000.00 |  |  | GES |  |  |  | World Vision |  |  |
|  | - Establish and ensure the proper functioning of SMCs and PTAs in all schools |  | District Wide | √ | Improved performance | √ | √ | √ |  | √ |  |  | 10,000.00 |  |  | GES |  |  |  | KADA |  |  |
|  | - Intensify supervision and monitoring of Teaching and Learning activities at all levels |  | District Wide | √ | Improved performance | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | GES |  |  |  | KADA |  |  |
|  | - Organize School Performance Appraisal meetings in the school communities (SPAM) |  | District Wide | √ | Improved performance | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | GES |  |  |  | KADA |  |  |
|  | - Monitor BECE and WASSCE and organise annual mock examinations |  | District Wide | √ | Improved BECE/ WASCE performance | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | GES |  |  |  | KADA |  |  |
|  | - Intensify school health and hygiene education activities in schools |  | District Wide | √ | Improved sanitation, health and hygiene | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | GES |  |  |  | KADA/WV |  |  |
|  | - Organize capacity training for head teachers and teachers |  | District Wide | √ | Improved capacity | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | GES |  |  |  | KADA |  |  |
|  | - Promote the construction of WASH facilities in schools |  | District Wide | 4 | Improvement in sanitation and hygiene | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | KADA |  |  |  | GES/WV |  |  |
|  | - Support annual teachers award scheme. |  | District Wide | √ | Enhanced quality of teaching and learning | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | GES |  |  |  | KADA |  |  |
|  | - Organize capacity training for staff of the education directorate |  | Kadjebi | √ | Enhanced quality of teaching and learning | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | GES |  |  |  | KADA |  |  |
|  | - Provide financial assistance to students studying science; technical, vocational programmes |  | District Wide | √ | Increased employment avenues | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | GES |  |  |  | BAC |  |  |
|  | - Provision of furniture to schools |  | District Wide | 400 | Enhanced quality of teaching and learning | √ | √ | √ |  | √ |  | 30,000.00 |  |  |  | KADA |  |  |  | GES |  |  |
| Safe and disciplined society | - Support security agencies to deliver services |  | Safe and disciplined society | √ | Improved security | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | GPS |  |  |  | KADA |  |  |
|  | - Support the effective resolution of chieftaincy disputes |  | District Wide | √ | Chieftaincy roles enhanced in the governance process | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | DISEC |  |  |  | DPCU |  |  |
|  | - Procure and supply Magistrate court with computer set and other office equipment’s |  | Kadjebi | - | Improved security | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | KADA |  |  |  | Magistrate court |  |  |
|  | - Construction District Police Headquarters |  | District Wide | - | Improved security | √ | √ | √ |  | √ |  |  |  |  |  | GPS |  |  |  | KADA |  |  |
| Public Health Services | - Completion of 1no. CHPS Compound |  | Menuso | 1 | Increased access to health services | √ | √ | √ |  | √ |  | 133,540.92 |  |  |  | KADA |  |  |  | Health Depart/Systems for Health |  |  |
|  | - Completion of 2No. Nurses Quarters |  | Asato, Pepesu |  | Enhanced Healthcare | √ | √ | √ |  | √ |  | 100,000 |  |  |  | MP |  |  |  | KADA |  |  |
|  | - Renovate and expand infrastructure in 1No. existing Health Centers |  | Dodo Amanfrom | - | Increased access to health services | √ | √ | √ |  | √ |  | 300,000.00 |  |  |  | KADA |  |  |  | Health Depart |  |  |
|  | - Support routine immunizations programmes e.g Polio |  | District Wide | √ | Healthy societies | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | Health Depart |  |  |  | KADA |  |  |
|  | - Procurement of Covid-19 PPEs |  | Kadjebi |  | Covid 19 PPEs procured | √ |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  | KADA |  |  |
|  | - Support Malaria control programme |  | District Wide | √ | Healthy societies | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | Health Depart |  |  |  | KADA |  |  |
|  | - Support mental health promotion activities |  | District Wide | √ | Improved health care delivery | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | Health Depart |  |  |  | KADA |  |  |
|  | - Undertake HIV/AIDS activities and advocacy programmes with stakeholders |  | District Wide | √ | Reduction in HIV infections | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | Health Depart |  |  |  | KADA |  |  |
|  | - Organize 2No. Stigma reduction activities |  | District Wide | √ | Reduction in HIV infections | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | Health Depart |  |  |  | KADA |  |  |
|  | - Undertake Prevention of mother-to-child transmission of HIV activities |  | District Wide | √ | Reduction in HIV infections | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | Health Depart |  |  |  | KADA |  |  |
|  | - Undertake 2No food safety, nutrition education for the public and screening of food handlers |  | District Wide | √ | Improved Food safety | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | Health Depart |  |  |  | KADA/EHSD |  |  |
| Social Welfare and Community Development | - Undertake skills training in entrepreneurship and offer financial support to PWDs |  | District Wide | √ | Increased access to job opportunities for PWDs | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | SW/CD |  |  |  | Committee of PWDs |  |  |
|  | - Identify and train 20 persons in sign language interpretation |  | District Wide | - | Effective communication assured | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | SW/CD |  |  |  | Committee of PWDs |  |  |
|  | - Organize 2No advocacy programmes for PWDs |  | District Wide | 2 | Enhanced capacity of PWDs | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | SW/CD |  |  |  | Committee of PWDs |  |  |
|  | - Carry out family welfare and child rights protection and promotion services |  | District Wide | √ | Child protection systems strengthened | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | SW/CD |  |  |  | Committee of PWDs |  |  |
|  | - Support referral case management system |  | District Wide | - | Child protection systems strengthened | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | DCPC |  |  |  | SW/CD |  |  |
|  | - Supervise Day Care centres in the District. |  | District Wide | √ | Child rights protected | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | SW/CD |  |  |  | Committee of PWDs/KADA |  |  |
|  | - Collaborate with law enforcement agencies to intensify the fight against worst form of child labour, negative practices, child abuse and trafficking |  | District Wide | √ | Rights of children protected | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | SW/CD |  |  |  | Law enforcement agencies |  |  |
|  | - Offer financial support to brilliant but needy and vulnerable children in schools |  | District Wide | √ | Reduction in poverty | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | KADA |  |  |  | GES |  |  |
|  | - Support the expansion of LEAP to cover more persons in the District |  | District Wide | √ | Reduction in poverty | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | SW/CD |  |  |  | DPCU |  |  |
|  | - Mainstream gender issues into the development process of the District |  | District Wide | √ | Gender mainstreamed | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | SW/CD |  |  |  | DPCU |  |  |
| Environmental Health and Sanitation Services | - Organise Clean up exercises (National sanitation day) |  | District Wide | 12 | Improved sanitation | √ | √ | √ |  | √ |  |  | 2,000.00 |  |  | EHSU |  |  |  | KADA |  |  |
|  | - Community hygiene/Household and business education/prosecution |  | District Wide | 12 | Improved sanitation | √ | √ | √ |  | √ |  |  | 500.00 |  |  | EHSU |  |  |  | KADA |  |  |
|  | - Medical Screening of food vendors |  | District Wide | 12 | Improved sanitation | √ | √ | √ |  | √ |  |  | 5000.00 |  |  | EHSU |  |  |  | KADA |  |  |
|  | - Maintenance of animal pound |  | Kadjebi | 1 | Animal pound maintained | √ | √ | √ |  | √ |  |  | 500.00 |  |  | EHSU |  |  |  | KADA |  |  |
| U | - Update DESSAP |  |  |  |  |  |  |  |  |  |  | 5000.00 |  |  |  | EHSU |  |  |  | KADA |  |  |
|  | - Promote CLTS and SanMark activities |  | District Wide | √ | Increased access to household sanitation facilities | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | EHSU |  |  | UNICE |  |  |  |
|  | - Maintenance and repairs of Office equipment |  | District Wide | √ | Maintenance works carried out | √ | √ | √ |  | √ |  | 10,000.00 |  | 20,000.00 |  | EHSU |  |  |  | UNICEF/WV |  |  |
|  | - Undertake effective liquid and solid waste management activities |  | District Wide | √ | Improved solid and liquid waste management system | √ | √ | √ |  | √ |  | 20,000.00 |  | 30,000.00 |  | EHSU |  |  |  | UNICEF/WV |  |  |
|  | - Distribute waste bins to residents in the District |  | District Wide | 34 | Improved environmental sanitation | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | zoomlion |  |  |  | EHSU |  |  |
|  | - Undertake disinfestation and fumigation activities |  | District Wide | √ | Improved environmental sanitation | √ | √ | √ |  | √ |  | 200,000.00 |  |  |  | zoomlion |  |  |  | EHSU |  |  |
|  | - Procure sanitary tools and equipment |  | Kadjebi | √ | Improved environmental sanitation | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | KADA |  |  |  | EHSU |  |  |
|  | - Operation and maintenance of Cesspit emptier |  | Kadjebi | √ | Improved environmental sanitation | √ | √ | √ |  | √ |  | 5000.00 |  |  |  | KADA |  |  |  | EHSU |  |  |
|  | - Maintenance of final disposal site |  | Kadjebi | √ | Improved environmental sanitation | √ | √ | √ |  | √ |  | 200,000.00 |  |  |  | zoomlion |  |  |  | EHSU/KADA |  |  |
| GOAL 3: ENVIRONMENT,INFRASTRUCTURE AND HUMAN SETTLEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme 3: Infrastructure Development and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programmes | Activities (Operations) |  | Location | Baseline | Output Indicators | Quarterly Time schedule |  |  |  |  |  | Indicative Budget |  |  |  | Implementing Agencies |  |  |  |  |  |  |
|  |  |  |  |  |  | 1st | 2nd | 3rd |  | 4th |  | GoG | IGF | DONOR |  | Lead |  |  |  | collaborating |  |  |
| Infrastructure Development and Management/ Urban Roads and Transport Services | - Reshaping of 30km feeder roads |  | District Wide | 18 | Improved transportation systems | √ | √ | √ |  | √ |  | 30,000.00 |  |  |  | DWD |  |  |  | Urban Roads/ Ghana Highways Authority |  |  |
|  | - Spot improvement of 30km feeder roads |  | District Wide | - | Improved transportation systems | √ | √ | √ |  | √ |  | 50,000.00 |  |  |  | DWD |  |  |  | Urban Roads/ Ghana Highways Authority |  |  |
| Road Safety | - Institute sensitisation programmes on road use regulations among road users |  | District Wide |  | Improved road Safety | √ | √ | √ |  | √ |  | 60,000 |  |  |  | DWD |  |  |  |  |  |  |
|  | - Regular maintenance of road signage |  | District Wide |  |  | √ | √ | √ |  | √ |  | 20,000 |  |  |  | DWD |  |  |  |  |  |  |
|  | - Maintenance of grader |  | Kadjebi |  |  | √ | √ | √ |  | √ |  | 50,000 |  |  |  | DWD |  |  |  |  |  |  |
|  | - Collaborate with DVLA on issuance of licenses in Kadjebi quarterly |  |  |  |  | √ | √ | √ |  | √ |  | 2,000 |  |  |  | DWD |  |  |  |  |  |  |
|  | - Improve night visibility through installation and maintenance of street lights |  | District Wide |  |  | √ | √ | √ |  | √ |  | 70,000 |  |  |  | DWD |  |  |  | DWD |  |  |
| Spatial Planning | - Undertake regular development control activities |  | District Wide | √ | Well planned communities | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | PPD |  |  |  | DWD |  |  |
|  | - Procurement of Landscaping equipment |  | District Wide | √ | Well planned communities | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | PPD |  |  |  | DWD, GIZ |  |  |
|  | - Acquire land for establishment of New Lorry Station at Kadjebi |  | Kadjebi | - | Well planned communities | √ |  |  |  |  |  | 30,000.00 |  |  |  | KADA |  |  |  | PPD |  |  |
|  | - Undertake capacity building programmes for Physical Planning Department officers |  | Kadjebi | √ | Enhanced capacity of PPD officers | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | PPD |  |  |  | HR Unit, GIZ |  |  |
|  | - Undertake public sensitization programmes on Physical development |  | District Wide | √ | Well planned communities | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | PPD |  |  |  | ISD, GIZ |  |  |
|  | - Prepare structure and site plans for selected communities |  | District Wide | - | Well planned communities | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | PPD |  |  |  | DWD/EHSU |  |  |
|  | - Ensure proper acquisition, documentation and payment for government/ KADA acquired lands |  | District Wide | - | Secured government lands | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | PPD |  |  |  | DWD/EHSU |  |  |
|  | - Provide and maintain street lights in the District |  | District Wide | √ | Well secured communities | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | DWD |  |  |  | Assembly men |  |  |
|  | - Continue Street naming and property addressing system |  | District Wide | √ | Well planned communities | √ | √ | √ |  | √ |  | 50,000.00 |  |  |  | GIZ/PPD |  |  |  | KADA/DPCU |  |  |
|  | - Promote and construct 15No. boreholes in the District |  | District Wide | 12 | Improved access to potable water | √ | √ | √ |  | √ |  | 35,000.00 |  |  |  | DWD |  |  |  | DWST |  |  |
|  | - Rehabilitate 20No. boreholes in the District |  | District Wide | 15 | Improved access to potable water | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | DWD |  |  |  | DWST |  |  |
|  | - Review, gazette and enforce KADAs bye-laws on sanitation |  | District Wide | √ | Improved sanitation | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | KADA |  |  |  | EHSU |  |  |
|  | - Organize capacity programmes for actors in Water management |  | District Wide | √ | Improved access to potable water | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | KADA |  |  |  | HR/DWST |  |  |
|  | - Embark on regular monitoring of Water facility on quality, effective management and reporting mechanisms |  | District Wide | √ | Improved access to potable water | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | DWD |  |  |  | DWST |  |  |
| Improve the welfare and infrastructure for staff | - Prepare and implement operation and maintenance plan for the Assembly |  | District Wide | √ | Assembly properties maintained | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | KADA |  |  |  | DPCU |  |  |
|  | - Renovate 4No Assembly staff bungalows |  | Kadjebi | 3 | Enhanced staff welfare | √ | √ | √ |  | √ |  | 40,000.00 |  |  |  | DWD |  |  |  | DPCU |  |  |
|  | - Construction of fence wall and security post at DCE residency Building and other Security installations |  | Kadjebi |  | Enhanced staff welfare | √ | √ | √ |  | √ |  | 300,000.00 |  |  |  | DWD |  |  |  | DPCU |  |  |
|  | - Fencing of DCDs Bungalow |  | Kadjebi |  | Enhanced staff welfare | √ | √ | √ |  | √ |  | 80,000.00 |  |  |  | DWD |  |  |  | DPCU |  |  |
|  | - Renovate Assembly block, Assembly Hall and other Offices and departments |  | Kadjebi |  | Assembly properties maintained | √ | √ | √ |  | √ |  | 30,000.00 |  |  |  | DWD |  |  |  | DPCU |  |  |
|  | - Procure 1No. Power Generating Plant |  | Kadjebi |  | Enhanced productivity | √ | √ | √ |  | √ |  | 50,000.00 |  |  |  | KADA |  |  |  | DPCU |  |  |
| Environmental Management/ Natural Resource Conservation and Management | - Organize sensitization programmes on water resources protection |  | District Wide |  | Water resources protected | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | DWST |  |  |  | DPCU |  |  |
|  | - Support afforestation programmes along river basins |  | District Wide |  | Water resources protected | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | NADMO |  |  |  | YEA/NFS/EHSD/MoFA |  |  |
|  | - Facilitate Nursing and supply of Oil Palm seedlings to schools and communities |  | District Wide |  | Afforestation | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | NADMO |  |  |  | YEA/NFS/EHSD/MoFA |  |  |
|  | - Cultivate 10 ha Climate Oil Palm Plantation |  | Menuso |  | Climate Change activities carried out | √ | √ | √ |  | √ |  | 30,000.000 |  |  |  | GPSNP |  |  |  | KADA |  |  |
|  | - Cultivate 10 ha Climate Oil Palm Plantation |  | Titiaka |  |  |  |  |  |  |  |  | 30,000.000 |  |  |  | GPSNP |  |  |  | KADA |  |  |
|  | - Cultivate 10 ha Climate Change Cashew Plantation |  | Dodo Pepesu |  | Climate Change activities carried out | √ | √ | √ |  | √ |  | 300,000.00 |  |  |  | GPSNP |  |  |  | KADA |  |  |
|  | - Facilitate Nursing and supply of Teak Tree seedlings to schools and communities |  | District Wide |  | Afforestation | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | NADMO |  |  |  | YEA/NFS/EHSD/MoFA |  |  |
| Disaster Prevention and Management | - Undertake 2No capacity building programmes on climate change mitigation and adaptation |  | District Wide |  | Climate change impacts mitigated | √ | √ | √ |  | √ |  | 10,000.00 |  |  |  | NADMO |  |  |  | YEA/NFS/EHSD/MoFA |  |  |
|  | - Sensitize the public on disaster risk management and early warning systems |  | District Wide |  | Climate change impacts mitigated | √ | √ | √ |  | √ |  | 5,000.00 |  |  |  | NADMO |  |  |  | KADA |  |  |
|  | - Activation of fire volunteer groups |  | District Wide |  | Fire volunteer groups activated | √ | √ | √ |  | √ |  | 500.00 |  |  |  | NADMO |  |  |  | KADA |  |  |
|  | - Undertake disaster prevention activities (Hazard mapping, marking of dilapidated structures etc) |  | District Wide |  | Disaster prevention activities undertaken | √ | √ | √ |  | √ |  | 2000.00 |  |  |  | NADMO |  |  |  | KADA |  |  |
|  | - Supply relief items to disaster victims |  | District Wide |  | Reduced disaster impact | √ | √ | √ |  | √ |  | 20,000.00 |  |  |  | NADMO |  |  |  | KADA |  |  |