KADJEBI DISTRICT ASSEMBLY

2022 ANNUAL ACTION PLAN

PREPARED BY: DPCU, SEPTEMBER 2021

TABLE OF CONTENT

| ITEM | PAGE NUMBER |
| --- | --- |
| - INTRODUCTION | 2 |
| 1.1 BACKGROUND OF THE DISTRICT | 2 |
| OBJECTIVE OF THE PLAN | 3 |
| Methodology and Approach | 4 |
| Estimated Cost of the Plan | 4 |
| Work Plan (FRAMEWORK) | 5 |
| Ensuring And Sustaining Macroeconomic Stability | 5 |
| Enhancing competitiveness of Ghana private sector | 7-8 |
| Accelerated Agricultural Modernization and Sustainable Natural Resource Management | 9-10 |
| Infrastructure and Human Settlement Development | 10-13 |
| Human Development, Productivity and Employment | 14-16 |
| Transparent and accountable governance | 17-19 |

KADJEBI DISTRICT ASSEMBLY

ANNUAL ACTION PLAN FOR 2022

- INTRODUCTION

1.1 BACKGROUND OF THE DISTRICT

Kadjebi District was created as an Assembly by Legislative Instrument (L.I.) 1465 in 1989 and forms part of the 8 District and District Assemblies of the Oti Region of Ghana

The District is located South of the Oti Region of Ghana and forms part of the Eight (8) districts of the Region.  It is bordered to the north by Nkwanta South District, to the south by the Jasikan District, to the North West by Krachi East to the south east by Biakoye District. Kadjebi district has a long boarder eastwards with the by the Republic of Togo and has a total land area of 949 km2.  The strategic location of the district promotes cross border activities with the republic of Togo

The district has an average height of about 180 meters above sea level rising to about 600 meters towards the Ghana – Togo Border.  The district is blessed with beautiful landscape of hills, mountains and valleys.  The land form however is not a hindrance to road construction in the district.

The climate in the district is characterized by average monthly temperature of about 25oC and rainfall is between 1400 mm and 1800mm. Rainfall is generally heavy and starts from March and ends between October and November each year.  The peak of rainfall occurs in June.  These conditions are conducive for agriculture production. One major climatic problem, facing the district is severe rainstorms, which destroy farm crops, buildings and also cause severe soil erosion in some places especially during the rains.  Also, the prolonged drought during the dry season (December–March) is a major source of worry to farmers who are engaged in dry season agriculture production especially vegetables.

The Kadjebi district especially in the rainy season is generally green with trees covering beautiful landscape of mountains, hills and valleys. 90% of the district is predominantly covered with secondary rain forest.  The forests have economic trees such as wawa, mahogany, odum, red wood, raffia palm and bamboo grooves to support the wood processing industry.  Animal and bird species such as antelopes, monkeys, glasscutters,

weaverbirds and parrots abound in the forest.  The forest reserve with its animal and bird species is potential for eco-tourism development in the district.Activities such as hunting of animals, palm wine tapping and the method used in land clearing for farming cause bush fires which degrade the environment. Bush fire prone areas in the district include Todome, Dika, Ampeyo, Koru, Pampawie, Dapaa, Olobobi, Pepesu, Bekpo, Dodo-Bethel, Kadjebi, Dodo-Amanfrom and Dodo-Tamale.  The Ghana National Fire Service established at Kadjebi has a staff of twelve (12) personnel. Twenty-five (25) Fire Volunteers squads in the district have become dormant because they are not equipped and motivated to fight bush fires in the district.  The brand new Fire tender provided by government in 2012 is very effective in fighting in within the district and even beyond.

The total population of Kadjebi District is 59,303.  This is made up of 29,951 (51%) males and 29,303 (48.6%) females.

The Kadjebi District provides only 2.80% of the total Volta Region population for 2010.  The population growth rate of the district stands at 4.9%.  This is considered too high compared with the growth rates of 1.9% and 2.7% for the Region and the nation respectively.

The Kadjebi District Assembly’s 2018-2021 Medium Term  Development Plan was prepared in line with the Agenda for Jobs and it main focus is to address the economic imbalances and to build a robust economy with the possibility of sustaining an accelerated growth and poverty reduction towards archiving the Millennium Development Goals and middle income status. The objective of the Assembly is to implement policies and programmes outlined in the plan. And also effectively monitor implementation to archive expected output and outcomes which can inform future plans.

Objectives of the plan

The main purpose of the formulating annual action plan is to identify the sub project interventions for implementation in 2022. The plan was formed in line with Agenda for Jobs thematic area as follows:

- Economic Development

- Social Development

- Infrastructure and human settlement development

- Governance, Corruption and public Accountability

- Ghana’s role in international Affairs

Methodology and Approach

In preparing the annual work plan, these procedures were followed:

- A stakeholder’s workshop involving members of the expanded DPCU, traditional authorities, town/area councils and opinion leaders was held for the identification of sub-projects under various sources of funding. After discussions, brainstorming, and plenary sessions, sub projects were selected in accordance with the objectives and development needs of the people identified in the MTDP.

- There was also DPCU meeting to synthesize and finalize the document.

FUNDING SOURCES OF THE PLAN

District assembly common fund (DACF)    1,075,722.00

District development facility (DDF)        484,836.00

Internal generated fund (IGF)             340,986.52

Development partners (DP)               5,000.00

PWD                                 62,769.84

MPs Common Fund                     200,000.00

The estimates are however provisional and indicative, therefore they do not necessarily represent the actual cost of sub projects until the designs have been prepared for implementation.

Monitoring and evaluation

The District Planning Coordinating Units (DPCU) in cooperation with the DWD will be responsible for gathering data at the project sites by routine site visit and preparing and submitting quarterly report to VRCC in accordance with NDPC guidelines. Beneficiary community, institutions and other relevant staffs will be drawn into the monitoring team where appropriate. Data gathered at the district and zonal level will be disseminated and discussed at the learning and evaluation platforms to be established at the district and zonal level.

KADJEBI DISTRICT ASSEMBLY

| PROGRA MME (PBB) | SUB-PROGRAMME (PBB) | Projects/Activities | Outcome/Impact Indicators |  | Location | Time Frame |  |  |  | Cost |  |  | Program Status |  | Implement Inst/Dept. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GOG (GHȻ) | IGF/ ABFA(GHȻ) | OTHERS (GHȻ) | New | Ong. | Lead | Collab |
| ECONOMIC DEVELOPMENT | LOCAL ECONOMIC DEVELOPMENT | Facilitate market information flow by liasing SMEs with relevant stakeholders | Improved capacity of SMEs |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | BRC | KADA |
|  |  | Organize and introduce SMEs to trade fairs |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | BRC | KADA |
|  |  | Collect and update annually basic economic data on SMEs in the District | Improved access to economic data |  | District wide | √ | √ | √ | √ | 2,000 |  |  |  | √ | BRC | KADA |
|  |  | Organize 1No. capacity building training for exporters and potential exporters | Improved efficiency of SMEs |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | BRC | KADA |
|  |  | Establishment of 1No. Market | Increase in commercial activities |  | Pampawie | √ | √ | √ | √ | 200,000 |  |  |  | √ | KADA | DWD |
|  |  | Rehabilitation of 1No. Market |  |  | Ahamansu | √ | √ | √ | √ | 100,000 |  |  |  | √ | KADA | DWD |
|  |  | Establish network between SMEs and financial institutions | Improved capacity of SMEs |  | District wide | √ | √ | √ | √ | 1000 |  |  |  | √ | BRC | KADA |
|  |  | Promote the registration of businesses by SMEs |  |  | District wide | √ | √ | √ | √ | 1000 |  |  |  | √ | BRC | KADA |
|  |  | Organise 8No. training for 30 MSME’s on proper records keeping |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | BRC | KADA |
|  |  | Supply start-up kits to SMEs |  |  | District wide | √ | √ | √ | √ | 50,000 |  |  |  | √ | BRC | KADA |
|  |  | Support private sector to provide solar and biogas energy to communities | Increased access to alternative energy sources |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ |  |  |
|  |  | Facilitate the extension of electricity to under-served communities to promote development of businesses | Increased job opportunities |  | District wide | √ | √ | √ | √ | 5,000 |  |  | √ |  | KADA | ECG |
|  |  | Organize 4No. capacity training programmes in modern technology and value addition for exporters annually | Improved capacity of exporters |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | BRC | KADA |
|  |  | Facilitate the implementation of the “One District, One Factory programme | Reduction in youth unemployment |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | KADA |  |
|  |  | Partner private sector to undertake business development strategies |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | BRC | KADA |
|  |  | Support private sector involvement in Irrigation, fruits and vegetable farming, etc. |  |  | District wide | √ | √ | √ | √ | 2,000 |  |  |  | √ | BRC | KADA |
|  |  | Partner the private sector to develop, promote and create the tourism potentials in the District | Increase in revenue generation |  | District wide | √ | √ | √ | √ | 25,000 |  |  |  | √ | BRC | KADA |
|  | Agriculture | Partner the private sector to establish farm machinery mechanization centres | Improved capacity of staff for increased Agric productivity |  | District wide | √ | √ | √ | √ | 25,000 |  |  |  | √ | DDA | KADA |
|  |  | Organize training programmes for staff and farmers on rice and maize production |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Organize training programmes for staff and farmers on soil fertility management and fertilizer use |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Train Extension, veterinary staff and Livestock farmers in the prevention of scheduled livestock and local poultry diseases |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Organize training programmes for staff and farmers on farm planning and budget |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Facilitate public education on zoonotic diseases and carry out disease surveillance programmes | Minimise incidence of zoonotic diseases |  | District wide | √ | √ | √ | √ | 2,000 |  |  |  | √ | DDA | KADA |
|  |  | Organize training programmes for staff and farmers on principle of crops and livestock production | Increased crops and livestock production |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Undertake public education on food safety | Increase in rice production |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DDA | KADA |
|  |  | Facilitate the establishment of a rice value chain Platforms in the District | Increased agricultural productivity |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDA | KADA |
|  |  | Create and develop land banks for agricultural activities |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Develop and disseminate climate smart agricultural activities to farmers |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DDA | KADA |
|  |  | Partner the private sector to establish farm machinery mechanization centres |  |  | District wide | √ | √ | √ | √ | 50,000 |  |  |  | √ | DDA | KADA |
|  |  | Facilitate the feasibility study of 3 river bodies | Minimise incidence of post-harvest losses |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Train farmers and staff on storage of cereals | Increased agricultural productivity |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DDA | KADA |
|  |  | Supervise 20 demonstrations on proven rice and maize technologies in the District |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDA | KADA |
|  |  | Introduce improved planting materials ( ginger, cassava, oil palm and pineapple) to farmers |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DDA | KADA |
|  |  | Facilitate the supply of fertilizers to farmers |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DDA | KADA |
|  |  | vaccinate local poultry and small ruminants against schedule diseases | Increased poultry production |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Intensify the use of radio and for knowledge dissemination | Increased access to agriculture information |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDA | KADA |
|  |  | Carry out field and home visits by Technical Staff |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DDA | KADA |
|  |  | Carry out anti-rabies campaign | Minimise incidence of rabies |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDA | KADA |
|  |  | Carryout planting of food and job and Rearing for Food and job activities | Increase in yield per acre |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDA | KADA |
|  |  | Organise 4No. Capacity building for 500No. farmers |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDA | KADA |
|  |  | Undertake 4No. Monitoring and Evaluation on the programme |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDA | KADA |
|  |  | Facilitate the feasibility study of 3 river bodies |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DDA | KADA |
|  |  | - Renovation of AEA Bungalow at Pampawie | Increase in agricultural output |  | Pampawie | √ | √ | √ | √ | 10,000 |  |  | √ |  | DDA | KADA |
|  |  | Partner the private sector to establish farm machinery mechanization centres | Increase in ginger production |  | District wide | √ | √ | √ | √ | 15,000 |  |  | √ |  | DDA | KADA |
| Social Development | Education, youth & Sports | Construction of Urinal and Toilet for 2 No. Basic Schools | Increased school enrolment |  | Kadjebi DA ‘B’, Sumanten DA | √ | √ | √ | √ | 200,000 |  |  | √ |  | DWE | KADA |
|  |  | Renovation of 2No. Basic Schools |  |  | Kadjebi LA JHS, Papase R/C KG | √ | √ | √ | √ | 400,000 |  |  | √ |  | DWE | KADA |
|  |  | Construction of 1No. 3Unit JHS Block with Ancillary facilities |  |  | Pepesu LA | √ | √ | √ | √ | 400,000 |  |  | √ |  | DWE | KADA |
|  |  | Construction of 2No. 3Unit KG Blocks with Ancillary facilities |  |  | Okrakrom, Avornyokope | √ | √ | √ | √ | 400,000 |  |  | √ |  | DWE | KADA |
|  |  | Construction of 1No. 6Unit Block with Ancillary facilities |  |  | Kpomkpa | √ | √ | √ | √ | 600,000 |  |  | √ |  | DWE | KADA |
|  |  | Construction of 1No. 3Unit Classroom Block with Ancillary facilities |  |  | Dodo Amanfrom Islamic DA | √ | √ | √ | √ | 400,000 |  |  | √ |  | DWE | KADA |
|  |  | Construction of 2 No. 3unit teachers Bungalows |  |  | Menuso, Titiaka | √ | √ | √ | √ | 600,000 |  |  | √ |  | DWE | KADA |
|  |  | Renovation of 1No. teachers Bungalows |  |  | Asato | √ | √ | √ | √ | 40,000 |  |  | √ |  | DWE | KADA |
|  |  | Support school sports and cultural activities | Improved sports and culture activities |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DDE | KADA |
|  |  | Organize annual my First Day at School programmes | Increased school enrolment |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DDE | KADA |
|  |  | Support annual STME clinics | Improved results in STME |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDE | KADA |
|  |  | Provide material support(uniforms/shoes) to needy but brilliant students, especially Girls | Increased school enrolment Increased school enrolment |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDE | KADA |
|  |  | Provide financial support to needy but brilliant students, especially Girls |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDE | KADA |
|  |  | Facilitate career guidance in schools |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DDE | KADA |
|  |  | Establish and ensure the proper functioning of SMCs and PTAs in all schools | Improved basic education output |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DDE | KADA |
|  |  | Supervision, data collection and monitoring of Teaching and Learning activities at all levels |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDE | KADA |
|  |  | Organise School Performance Appraisal meetings in the school communities (SPAM) |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDE | KADA |
|  |  | Monitor BECE and WASSCE and organise annual mock examinations | Improved BECE and WASSCE results |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDE | KADA |
|  |  | Intensify school health and hygiene education activities in schools | Improved hygiene in schools |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DDE | KADA |
|  |  | Organize capacity training for head teachers and teachers | Improved basic education output |  | Kadjebi | √ | √ | √ | √ | 15,000 |  |  |  | √ | DDE | KADA |
|  |  | Institute annual teachers award scheme. |  |  | Kadjebi | √ | √ | √ | √ | 50,000 |  |  |  | √ | DDE | KADA |
|  |  | Organize capacity training for staff of the education directorate |  |  | Kadjebi | √ | √ | √ | √ | 5,000 |  |  |  | √ | DDE | KADA |
|  | Health Delivery Services | Support routine immunizations programmes e.g Polio | Improved health care delivery Improved health care delivery |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DHD | KADA |
|  |  | Support routine immunizations programmes e.g Polio |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DHD | KADA |
|  |  | Support Malaria control programme |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DHD | KADA |
|  |  | Support mental health promotion activities |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DHD | KADA |
|  |  | Undertake HIV/AIDS activities and advocacy programmes with stakeholders | Reduce the incidence of HIV/AIDS in the district |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DHD | KADA |
|  |  | Organize 12No. Stigma reduction activities |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DHD | KADA |
|  |  | Undertake Prevention of mother-to-child transmission of HIV activities |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DHD | KADA |
|  |  | Undertake 4No food safety education for the public and screening of food handlers | Improved food nutrition services |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DHD | KADA |
|  |  | Intensify nutrition education and promotion |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DHD | KADA |
|  |  | Support adolescent reproductive health |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DHD | KADA |
|  |  | Support expansion of family planning and nutrition education to rural Areas |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DHD | KADA |
|  |  | Support referral case management system | Improved health care delivery |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DHD | KADA |
|  |  | Construction of 2No. CHPS Compounds District wide | Improved health care delivery |  | Butabe, Dodo Tamale | √ | √ | √ | √ | 600,000 |  |  | √ |  |  |  |
|  |  | Completion of 1No. CHPS Compound |  |  | Dzindziso | √ | √ | √ | √ | 100,000 |  |  |  | √ | MP | KADA |
|  |  | Completion of 2No. Nurses Quarters |  |  | Asato, Pepesu | √ | √ | √ | √ | 200,00 |  |  |  | √ | MP | KADA |
|  | Social Welfare & Community Development | Undertake skills training in entrepreneurship and offer financial support to PLWDs | Increase job opportunities among PLWDs |  | District wide | √ | √ | √ | √ | 50,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Procure and white canes, crutches, wheelchairs and prosthetics to aid PLWDs mobility | Improved welfare of PLWDs |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Identify and train twenty(20) persons in sign language interpretation |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Institute special assistance for care givers of IDs and lepers |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Collect and collate data on all PWDs in the District | Improved information on PLWDs |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DSWCD | KADA |
|  |  | Implement PLWDs accessibility standards | Improved welfare of PLWDs |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DSWCD | KADA |
|  |  | Organize 4No advocacy programmes for PWDs |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Institute scholarship package for PLWDs education |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Facilitate in the recruitment of PLWDs in YEA and MASLOC models |  |  | District wide | √ | √ | √ | √ | 2000 |  |  |  | √ | DSWCD | KADA |
|  |  | Carry out family welfare and child rights protection and promotion services | Increased sensitisation on child rights and protection |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Carry out 8No education and sensitization programmes on the rights of the girl child | Reduce incidence of Child rights abuses |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Supervise Day Care centres in the District. |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Organize 6No public sensitization programmes on child protection |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Collaborate with law enforcement agencies to intensify the fight against worst form of child labour, negative practices, child abuse and trafficking |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Offer financial support to brilliant but needy and vulnerable children in schools | Improved welfare of vulnerable children |  | District wide | √ | √ | √ | √ | 50,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Support referral case management system | Improved case referral management |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DSWCD | KADA |
|  |  | Support the expansion of LEAP to cover more persons in the District | Improved welfare of the poor and vulnerable |  | District wide | √ | √ | √ | √ | 50,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Facilitate the registration and renewal of the aged and indigent on NHIS |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DSWCD | KADA |
|  |  | Train Social Welfare and Probing Officers on Juvenile case management and Standard Operating Procedures | Improved Child welfare outcomes |  | Kadjebi | √ | √ | √ | √ |  | 5,000 |  |  |  | DSW&CD, KADA | GIZ |
|  |  | Organise training session for decentralised departments and sub-structures on vulnerability /Gender responsive planning and budgeting | Enhanced staff capacity on vulnerability planning and busgeting |  | Kadjebi | √ | √ | √ | √ |  | 3,000 |  |  |  | DSW&CD, KADA | GIZ |
|  |  | Mainstream gender issues into the development process of the District |  | Improved welfare of women | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DSWCD | KADA |
|  |  | Empower women to take up leadership positions |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DSWCD | KADA |
|  |  | Undertake skills training and entrepreneurship and apprenticeship programmes for women |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  | √ |  | DSWCD | KADA |
|  |  | Formation of Child Protection in all Communities | Improved welfare of vulnerable children |  | District wide | √ | √ | √ | √ | 10,000 |  |  | √ |  | DSWCD | KADA |
|  | Environmental Health and Sanitation Services | Promote the construction of 800No. household latrines | Improved sanitation and hygiene practicesEnhanced staff capacity on project management |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DEHU | KADA |
|  |  | Promote the construction of 12No. institutional latrines in schools |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DEHU | KADA |
|  |  | Promote the franchise of 8No. public latrines in the District |  |  | District wide | √ | √ | √ | √ | 2,000 |  |  |  | √ | DEHU | KADA |
|  |  | Promote sanitation marketing activities |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DEHU | KADA |
|  |  | Convert 80 communities to ODF status |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DEHU | KADA |
|  |  | Implement ODF plan of the district |  |  | District wide | √ | √ | √ | √ | 25,000 |  |  |  | √ | DEHU | KADA |
|  |  | Sensitization of 800No. households on Household water treatment and safe storage |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DEHU | KADA |
|  |  | Promote hand washing with soap/ash in 800 households |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DEHU | KADA |
|  |  | Organize capacity training for 200 stakeholders and staff in sanitation and hygiene |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DEHU | KADA |
|  |  | Review, gazette and enforce KADAs bye-laws on sanitation |  |  | Kadjebi | √ | √ | √ | √ | 5,000 |  |  |  | √ | DEHU | KADA |
|  |  | Review, update and implement the DESSAP |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DEHU | KADA |
|  |  | Undertake effective liquid and solid waste management activities |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DEHU | KADA |
|  |  | Organize award scheme for ODF communities |  |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | DEHU | KADA |
|  |  | Distribute waste bins to residents in the District |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DEHU | KADA |
|  |  | Undertake disinfestation activities |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DEHU | KADA |
|  |  | Procure sanitary tools and equipment |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DEHU | KADA |
|  |  | Complete acquisition of final disposal site |  |  | District wide | √ | √ | √ | √ | 100,000 |  |  |  | √ | DEHU | KADA |
|  |  | Maintenance of solid and liquid final disposal site |  |  | District wide | √ | √ | √ | √ | 25,000 |  |  |  | √ | DEHU | KADA |
|  |  | Acquisition and Provision of Refuse Containers for selected communities district wide |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DEHU | KADA |
|  |  | Enforcement of By-laws on Stray animals |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  | √ |  | DEHU | KADA |
| Infrastructure and Human Settlements Development | Urban Roads and Transport Services | Reshaping of 30km feeder roads | Improved road transport |  | District wide | √ | √ | √ | √ | 500,000 |  |  | √ |  | DWD | KADA |
|  |  | Establishment of 1No. Lorry station complex |  |  | District wide | √ | √ | √ | √ | 800,000 |  |  | √ |  | DWD | KADA |
|  |  | Spot improvement of 25km feeder roads |  |  | District wide | √ | √ | √ | √ | 200,000 |  |  | √ |  | DWD | KADA |
|  |  | Construction of 1 No. foot bridge on the Dubonku Stream | Improved protection of human and built environment |  | Kadjebi | √ | √ | √ | √ | 100,000 |  |  | √ |  | DWD | KADA |
|  |  | Construct of 1No. Drains district wide |  |  |  | √ | √ | √ | √ | 100,000 |  |  | √ |  | DWD | KADA |
|  |  | Rehabilitation of Drains at Kadjebi Bank Squre |  |  | Kadjebi | √ | √ | √ | √ | 100,000 |  |  | √ |  | DWD | KADA |
|  | Road Safety | Institute sensitisation programmes on road use regulations among road users | Improved adherence to road use regulations |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  |  | KADA | Ghana Police |
|  |  | Collaborate with DVLA on issuance of licenses in Kadjebi quarterly | Increased discipline among vehicle owners |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  |  | KADA | DVLA |
|  |  | Improve night visibility through installation and maintenance of street lights | Improved satety on the roads |  | District wide | √ | √ | √ | √ | 25,000 |  |  |  |  | DWD | KADA |
|  |  | Regular maintenance of road signages |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  |  | DWD | KADA |
|  |  | Encourage the use of approved bus stops along the major roads in the district |  |  | District wide | √ | √ | √ | √ | 5000 |  |  |  |  | KADA | Ghana Police, GRSA |
|  | Public Works, Rural Housing and Water Management | Promote and construct 1No. pipe schemes in the District | Increased access to improved water sources |  | Dodo Amanfrom | √ | √ | √ | √ | 200,000 |  |  | √ |  | DWD | KADA |
|  |  | Promote and construct 10No. boreholes in the District |  |  | District wide | √ | √ | √ | √ | 100,000 |  |  | √ |  | DWD | KADA |
|  |  | Rehabilitate 1No. pipe schemes in the District |  |  | Asato | √ | √ | √ | √ | 100,000 |  |  |  | √ | DWD | KADA |
|  |  | Rehabilitate 20No. boreholes in the District |  |  | District wide | √ | √ | √ | √ | 80,000 |  |  | √ |  | DWD | KADA |
|  |  | Advertise and implement District Water and Sanitation Plan (DWSP) |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  | √ |  | DWD | KADA |
|  |  | Organize capacity programmes for actors in Water management |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DWD | KADA |
|  |  | Embark on regular monitoring of Water facility on quality, effective management and reporting mechanisms |  |  | District wide | √ | √ | √ | √ | 20,000 |  |  |  | √ | DWD | KADA |
|  |  | Prepare and implement operation and maintenance plan for the Assembly | Improved staff output |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DWD | KADA |
|  |  | Renovate 2No Assembly staff bungalows |  |  | Kadjebi | √ | √ | √ | √ | 80,000 |  |  |  | √ | DWD | KADA |
|  |  | Undertake revaluation of all Assembly assets |  |  | Kadjebi | √ | √ | √ | √ | 10,000 |  |  |  | √ | DWD | KADA |
|  |  | Renovate Assembly block, Assembly Hall and other Offices |  |  | Kadjebi | √ | √ | √ | √ | 80,000 |  |  |  | √ | DWD | KADA |
|  |  | Acquire land for establishment of cemetery at Kadjebi | Improved land use planning |  | Kadjebi | √ | √ | √ | √ |  | 50,000 |  | √ |  | DWD | KADA |
|  | Land Use and Spatial Planning | Undertake regular site inspection of development activities | Improved spatial and development control |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | PPD | KADA |
|  |  | Enforce by-laws on physical developments |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | PPD | KADA |
|  |  | Undertake capacity building programmes for Physical Planning Department officers | Increased Capacity for staff in land use planning |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | PPD | KADA |
|  |  | Undertake public sensitization programmes on Physical development | Increased adherence to land use planning |  | District wide | √ | √ | √ | √ |  | 5,000 |  |  | √ | PPD | KADA |
|  |  | Prepare structure and site plans for selected communities |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | PPD | KADA |
|  |  | Train members of statutory planning committee on spatial planning | Increased Capacity for key actors in land use planning |  | District wide | √ | √ | √ | √ |  | 5,000 |  |  | √ | PPD | KADA |
|  |  | Training of PPD staff in upgrading address maps into approved local plans | Improved land use planning |  | Kadjebi | √ | √ | √ | √ |  | 1,000 |  |  |  | PPD, KADA | GIZ |
|  |  | Consultation and validation of Communities on street names (For Asato Community and part of Kadjebi) | Enhanced Street addressing system |  | Kadjebi, Asato | √ | √ | √ | √ | 5,000 |  |  |  |  | PPD, KADA | GIZ |
|  |  | Stenciling of 2600 house numbers (About 1600 properties in Kadjebi and 1000 for Asato) | Enhanced Property addressing system |  | Kadjebi, Asato | √ | √ | √ | √ | 17,000 |  |  |  |  | PPD, KADA | GIZ |
|  |  | Ensure proper acquisition, documentation and payment for government/ KADA acquired lands | Improved protection of public lands |  | District wide | √ | √ | √ | √ | 25,000 |  |  |  | √ | PPD | KADA |
|  |  | Continue Street naming and property addressing system | Improved land use planning |  | District wide | √ | √ | √ | √ | 25,000 |  |  |  | √ | PPD | KADA |
|  | Natural Resource Conservation and Management | Organize sensitization programmes on water resources protection | Improved conservation of natural resources |  | District wide | √ | √ | √ | √ | 2,500 |  |  |  | √ | NADMO | KADA |
|  |  | Support afforestation programmes along river basins |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | NADMO | KADA |
|  |  | Organize sensitization programmes on the protection of biodiversity |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | NADMO | KADA |
|  |  | Organize sensitization programmes to Promote the use of environmentally friendly methods and products |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | NADMO | KADA |
|  |  | Organize 4No. Public sensitization programmes on the conservation of wildlife resources |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | NADMO | KADA |
|  | Disaster Prevention and Management | Undertake 4No capacity building programmes on climate change mitigation and adaptation | Minimise the incidence of natural and man-made disasters |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | NADMO | KADA |
|  |  | Promote tree planting activities |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | NADMO | KADA |
|  |  | Organize 6No. Sensitization on disaster risk management and early warning systems |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | NADMO | KADA |
|  |  | Supply relief items to disaster victims |  |  | District wide | √ | √ | √ | √ | 100,000 |  |  |  | √ | NADMO | KADA |
|  |  | Construct 2No. mechanised dedicated Boreholes for fire service use |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | NADMO | KADA |
| Management and Administration | Planning, Budgeting, Statistics, Monitoring and Evaluation | Ensure participation of civil society in M&E activities and other public events | Improved citizen involvement in development |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Organize radio programmes to educate the public on activities of the Assembly |  |  | District wide | √ | √ | √ | √ | 15,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Involve stakeholders in fee fixing and budget preparations |  |  | District wide | √ | √ | √ | √ | 50,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Prepare and submit 1No. Annual Action Plans | Improve transparency and accountabilityImproved planning outcomes |  | Kadjebi | √ | √ | √ | √ | 20,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Organise district based technical support for plan review and collaborate with NDPC to organise regional base draft plan reviews |  |  | Kadjebi | √ | √ | √ | √ | 14,500 |  |  |  |  | DPCU, KADA | GIZ |
|  |  | Prepare and Submit 5No. Progress Reports |  |  | Kadjebi | √ | √ | √ | √ | 15,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Organise 1No. Mid year review of Composite Annual Action Plan and Budget |  |  | Kadjebi | √ | √ | √ | √ | 15,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Organize 1No. training programmes for planning stakeholders |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Disseminate the results of the 2021 PHC exercise | Enhanced data quality |  | District wide | √ | √ | √ | √ | 8,000 |  |  |  | √ | DPU, DBU | KADA |
|  |  | Collection of data and development of District Database |  |  | District wide | √ | √ | √ | √ | 5,500 |  |  |  | √ | DPU, DBU | KADA |
|  | Human Resource Management | Organize 1No. capacity training for Town/Area council staffs | Increased staff output and efficiency |  | Kadjebi | √ | √ | √ | √ | 20,000 |  |  |  | √ | HRD | KADA |
|  |  | Recruit and train 50 commission collectors for Town/Area councils |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | HRD | KADA |
|  |  | Organize 1No. capacity training programmes for revenue and finance staff in revenue mobilization strategies annually |  |  | Kadjebi | √ | √ | √ | √ | 5,000 |  |  |  | √ | HRD | KADA |
|  |  | Organize and support staff to undertake capacity building programmes |  |  | Kadjebi | √ | √ | √ | √ | 15,000 |  |  |  | √ | HRD | KADA |
|  |  | Organise workshop for Heads of Departments and relevant staff of MMDAs on Project Management and Report writing | Enhanced staff capacity on project management |  | Kadjebi | √ | √ | √ | √ | 7,500 |  |  |  | √ | DPCU, KADA | GIZ |
|  |  | Organise training on the roles and responsibilities of assembly members and sub-structures with focus on planning and budgeting. (Acts and L.I.) |  |  | Kadjebi | √ | √ | √ | √ | 6300 |  |  |  | √ | DPCU, KADA | GIZ |
|  |  | Organize 1No. capacity training programmes for DPCU on O&M, Procurement, assets and project Mgt. |  |  | Kadjebi | √ | √ | √ | √ | 5,000 |  |  |  | √ | HRD | KADA |
|  |  | Organize 1No. capacity training programmes on LGS Protocols |  |  | Kadjebi | √ | √ | √ | √ | 10,000 |  |  |  | √ | HRD | KADA |
|  | Finance | Prepare and implement 1No. Revenue Improvement Action Plan | Increase in IGF by the Assembly |  | Kadjebi | √ | √ | √ | √ | 10,000 |  |  |  | √ | DFD | KADA |
|  |  | Carry out Regular sensitisation campaigns on tax obligations by citizens |  |  | District wide | √ | √ | √ | √ | 5,000 |  |  |  | √ | DFD | KADA |
|  |  | Make contractual arrangement with 3No. Telecom providers to enable text messaging options | Improved IGF generation |  | District wide | √ | √ | √ | √ |  | 1,500 |  |  |  | DFD, KADA | GIZ |
|  |  | Develop and implement Bill Printing Plan |  |  | Kadjebi | √ | √ | √ | √ |  | 250 |  |  |  | DFD, KADA | GIZ |
|  |  | Develop and implement revenue collection plan |  |  | Kadjebi | √ | √ | √ | √ |  | 3,700 |  |  |  | DFD, KADA | GIZ |
|  |  | Conduct 2No. joint activities on rate / taxpayer education |  |  | Kadjebi | √ | √ | √ | √ |  |  |  |  |  | DFD, KADA | GIZ |
|  |  | Hold 4No. quarterly meetings with GRA to discuss joint activities / monitor progress |  |  | Kadjebi | √ | √ | √ | √ |  | 2,200 |  |  |  | DFD, KADA | GIZ |
|  |  | Promote inclusion in FFR consultations |  |  | Kadjebi | √ | √ | √ | √ | 11,500 |  | 11,500 |  |  | DPCU, KADA | GIZ |
|  |  | Conduct 2No.Sensitisation of citizens on Revenue collection/tax education, tax compliance |  |  | District Wide | √ | √ | √ | √ |  | 6,000 |  |  |  | PPD, KADA | GIZ |
|  | Accountability and Anti-Corruption | Prepare and implement KADAs NACAP Activities | Increased transparency and accountability |  | Kadjebi | √ | √ | √ | √ | 50,000 |  |  |  |  | DCA | KADA |
|  |  | Support 4No. Internal field Audits/monitoring of projects |  |  | District wide | √ | √ | √ | √ | 4,600 |  |  |  |  | IAU,KADA | GIZ |
|  |  | Support to Social Audit Committees to embark on 4No. project audit in their communities |  |  | District wide | √ | √ | √ | √ | 6,500 |  |  |  |  | IAU,KADA | KADA |
|  |  | Support to CSOs and marginalized groups by providing a platform for exchange of information between citizens and local government officials |  |  | District wide | √ | √ | √ | √ | 18,500 |  |  |  |  | KADA | GIZ |
|  |  | Organize 4No. annual Town Hall meetings and other public forums at Area Council levels |  |  | District wide | √ | √ | √ | √ | 100,000 |  |  |  |  | DCA | KADA |
|  |  | Organize public education and awareness programmes for the general public on Anti-Corruption |  |  | District wide | √ | √ | √ | √ | 60,000 |  |  |  |  |  |  |
|  |  | Hold regualr Collaborations with Civil Societies in anti-corruption |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  |  |  |  |
|  |  | Strengthen internal control measures to reduce opportunities for corruption. |  |  | District wide | √ | √ | √ | √ | 10,000 |  |  |  |  |  |  |
|  | Central Admin | Celebrate National and International Anniversaries/ Days and events | Improved citizen participation |  |  | √ | √ | √ | √ | 25,000 |  |  |  | √ | DCA | KADA |
|  |  | Organize 4No Inter-Service & Sectorial Collaboration & Cooperation System (ISCCS) meetings | Increase in inter-Sectoral collaborations |  |  | √ | √ | √ | √ | 5,000 |  |  |  | √ | DCA | KADA |
|  |  | Support the effective resolution of chieftaincy disputes | Improved security in the district |  |  | √ | √ | √ | √ | 5,000 |  |  |  | √ | DCA | KADA |
|  |  | Support culture activities of the various traditional Councils | Promote indigenous arts and culture |  |  | √ | √ | √ | √ | 5,000 |  |  |  | √ | DCA | KADA |
|  |  | Implement the DAs NACAP Activities | Increased transparency and accountability |  |  | √ | √ | √ | √ | 2,500 |  |  |  | √ | DCA | KADA |
|  |  | Procure and maintain office equipment, logistics and stationery | Improved staff output |  |  | √ | √ | √ | √ | 20,000 |  |  |  | √ | DCA | KADA |
|  |  | Procure and supply office equipment, logistics and stationery to Area Councils |  |  |  | √ | √ | √ | √ | 20,000 |  |  |  | √ | DCA | KADA |
|  |  | Implement the District Workplace Safety Plan |  |  |  | √ | √ | √ | √ | 5,000 |  |  |  | √ | DCA | KADA |

COMPOSITE 2022 ANNUAL ACTION PLAN