TABLE 69: DISTRICT COMPOSITE ANNUAL ACTION PLAN 2020

| Goal 4. GOVERNANCE, CORRUPTION AND ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme 1: Management and Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programmes |  | Activities (Operations) |  |  |  | Location |  |  | Baseline |  |  | Output Indicators |  |  | Quarterly Time schedule |  |  |  |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st |  |  | 2nd |  | 3rd |  |  | 4th |  |  | GoG |  |  | IGF |  |  |  | DONOR |  |  |  | Lead |  |  | collaborating |  |  |  |  |  |  |
| General Administration |  | Organize 4No Inter-Service & Sectorial Collaboration & Cooperation System (ISCCS) meetings |  |  |  | Kadjebi |  |  | √ |  |  | Organize Inter-Service & Sectorial Collaboration & Cooperation System (ISCCS) meeting |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 4,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR |  |  |  |  |  |  |
|  |  | Involve TAs in decision making processes of the Assembly |  |  |  | Kadjebi |  |  | √ |  |  | TAs involved decision making processes of the Assembly |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 6,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR |  |  |  |  |  |  |
|  |  | Embark on participatory M&E activities on development projects |  |  |  | District Wide |  |  | √ |  |  | Improved engagement of CSOs in public policy making |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  |  | DPCU |  |  | Relevant stakeholders |  |  |  |  |  |  |
|  |  | Organize radio programmes to educate the public on activities of the Assembly |  |  |  | District Wide |  |  | √ |  |  | Improved access of the public to the Assembly |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | DPCU |  |  | Relevant stakeholders |  |  |  |  |  |  |
|  |  | Implement the popular participation strategy of the Assembly |  |  |  | District Wide |  |  | √ |  |  | Popular participation strategy of the Assembly implemented |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 9,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Ensure effective operationalization of the client service unit |  |  |  | DA |  |  | √ |  |  | Effective operationalization of the client service unit ensured |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Celebrate 5No. National and International Anniversaries/ Days and events annually |  |  |  | District Wide |  |  | 5 |  |  | National and International days celebrated |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 13,000.00 |  |  |  |  |  |  | 20,000.00 |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Procurement of office supplies and consumables |  |  |  | DA/Area Councils |  |  | √ |  |  | Office supplies and consumables supplied |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 20,000.00 |  |  | 10,000.00 |  |  |  |  |  |  |  | KADA |  |  | PO/ DPCU |  |  |  |  |  |  |
|  |  | Organize 6No. annual Town Hall meetings and other public forums at Area Council levels |  |  |  | District |  |  | 4 |  |  | Town hall meetings organized |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Support other decentralized departments |  |  |  | District Wide |  |  | √ |  |  | Other decentralized departments supported |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  |  |  |  | 50,000.00 |  |  |  |  |  |  |  | KADA |  |  | DPCU |  |  |  |  |  |  |
|  |  | Support the operationalization of KADA’s ICT platforms and internet services. |  |  |  | Kadjebi |  |  | - |  |  | Increased access to ICT |  |  |  |  |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | DPCU |  |  |  |  |  |  |
|  |  | Support Assembly's meetings/workshops/seminars |  |  |  | Kadjebi |  |  | √ |  |  | Meetings/workshops/seminars held |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 15,000.00 |  |  | 20,000.00 |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Internal management of the Assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 200,000.00 |  |  |  |  |  |  |  | KADA |  |  | DPCU |  |  |  |  |  |  |
|  |  | Provision for any unplanned activity/Government directive |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 150,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | DPCU |  |  |  |  |  |  |
|  |  | Provide office furniture and fittings |  |  |  | DA/Area councils |  |  | √ |  |  | Furniture and fittings procured |  |  | √ |  |  |  |  |  |  |  |  |  |  | 12,000.00 |  |  | 20,000.00 |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
| Planning and Budgeting |  | Undertake quarterly monitoring and evaluation of development projects |  |  |  | Kadjebi |  |  | √ |  |  | Monitoring conducted |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | DPCU |  |  |  |  |  |  |
|  |  | Facilitate the preparation of 2021 fee fixing, Annual action plan and composite budget |  |  |  | Kadjebi |  |  | 3 |  |  | 2019 fee fixing, Annual action plan and composite budget prepared |  |  |  |  |  |  |  | √ |  |  | √ |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  | DPCU |  |  | CSOs |  |  |  |  |  |  |
|  |  | Organize capacity training programmes for DPCU on O&M, Procurement, assets and project management |  |  |  | Kadjebi |  |  | √ |  |  | Capacity training programmes for DPCU carried out |  |  |  |  |  |  |  | √ |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  | DPCU |  |  | HR |  |  |  |  |  |  |
| Finance |  | Organize 4No. Public sensitization on tax obligation |  |  |  | District Wide |  |  | 2 |  |  | IGF increased by 10% |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  | Finance Dept. |  |  | Budget Unit/ F&A Sub-Committee |  |  |  |  |  |  |
|  |  | Procure 1No. Pick Up vehicle for revenue mobilization |  |  |  | KADA |  |  | - |  |  | Pick Up procured |  |  | √ |  |  |  |  |  |  |  |  |  |  | 140,000.00 |  |  |  |  |  |  |  |  |  |  | Tender Committee |  |  | F&A Sub-Committee |  |  |  |  |  |  |
|  |  | Organize 12No. supervision of all revenue collections |  |  |  | District Wide |  |  | 5 |  |  | Increased revenue generation |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Finance Dept. |  |  | Budget Unit/ F&A Sub-Committee |  |  |  |  |  |  |
|  |  | Recruit and train 20 commission collectors for Town/Area councils |  |  |  | District Wide |  |  | 12 |  |  | Increased revenue generation |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 15,000.00 |  |  |  |  |  |  |  |  |  |  | Finance Dept. |  |  | F&A Sub-Committee |  |  |  |  |  |  |
|  |  | Organize 1No. capacity training programmes for revenue and finance staff in revenue mobilization strategies |  |  |  | Kadjebi |  |  | 1 |  |  | Improved revenue generation capacity |  |  |  |  |  | √ |  |  |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Finance Dept. |  |  | F&A Sub-Committee |  |  |  |  |  |  |
|  |  | Payment for accounting software |  |  |  | Kadjebi |  |  | - |  |  | Accounting software procured |  |  |  |  |  | √ |  |  |  |  |  |  |  | 12,000.00 |  |  |  |  |  |  |  |  |  |  | DFO |  |  | DPCU |  |  |  |  |  |  |
|  |  | Carry out Revaluation of properties in the District |  |  |  | District Wide |  |  | - |  |  | All properties revaluated |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | Lands Commission |  |  |  |  |  |  |
|  |  | Valuation of all fixed assets |  |  |  | District Wide |  |  | - |  |  | All fixed assets valuated |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 50,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | Lands Commission |  |  |  |  |  |  |
|  |  | Data collection to update business register of the District |  |  |  | District Wide |  |  | √ |  |  | % increase in revenue generation |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Finance Dept. |  |  | Budget Unit/ F&A Sub-Committee |  |  |  |  |  |  |
|  |  | Implementation of the 2020 Revenue Improvement Action Plan (RIAP) |  |  |  | District Wide |  |  | √ |  |  | Revenue performance enhanced |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  | DPCU |  |  | Revenue Unit |  |  |  |  |  |  |
| Human Resource |  | Organize and support staff to undertake capacity building programmes |  |  |  | District Wide |  |  | √ |  |  | Enhanced staff performance |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Organize 2No. capacity training programmes for DPCU on O&M, Procurement, assets and project Mgt. |  |  |  | Kadjebi |  |  | √ |  |  | Enhanced staff performance |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Organize 2No. capacity training programmes for Assembly Members/ Unit Committees/ Area Councils |  |  |  | District Wide |  |  | √ |  |  | Enhanced performance |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Procure and maintain office equipment, logistics and stationery |  |  |  | Kadjebi |  |  | √ |  |  | Enhanced staff performance |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | PO |  |  | DPCU |  |  |  |  |  |  |
|  |  | Procure and supply office equipment, logistics and stationery to Area Councils |  |  |  | District Wide |  |  | √ |  |  | Enhanced staff performance |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | PO |  |  | DPCU |  |  |  |  |  |  |
|  |  | Organize 2No. capacity training programmes on LGS Protocols |  |  |  | Kadjebi |  |  | √ |  |  | Enhanced staff performance |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
|  |  | Implement the District Workplace Safety Plan |  |  |  | District Wide |  |  | √ |  |  | Enhanced staff performance |  |  | √ |  |  | √ |  | √ |  |  | √ |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/ DPCU |  |  |  |  |  |  |
| GOAL 1: ECONONMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme 4: Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development |  | Rehabilitation and fencing of slaughter house |  |  |  | Kadjebi |  |  | - |  |  | Improved meat hygiene and job creation |  |  | √ |  |  |  |  |  |  |  |  |  |  |  |  | 140,000.00 |  |  |  |  |  |  |  |  | KADA |  |  | EHSU |  |  |  |  |  |  |
|  |  | Create Local Economic Platform for SMEs and financial institutions |  |  |  | District Wide |  |  | - |  |  | Increased access to market |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | BAC |  |  | DPCU |  |  |  |  |  |  |
|  |  | Establishment of 3No. Market |  |  |  | Pampawie, Papase, Poase Cement and Mempeasem |  |  | - |  |  | Increased access to market |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 60,000.00 |  | 20,000.00 |  |  |  |  |  |  |  |  | KADA |  |  | Community members |  |  |  |  |  |  |
|  |  | Rehabilitation of 4No. Market infrastructure |  |  |  | Kadjebi, Poase cement, Ahamansu and Amanfrom |  |  | - |  |  | Increased commercial activities |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | Community members |  |  |  |  |  |  |
|  |  | Organise 2No. training for 30 MSME’s on proper records keeping |  |  |  | District Wide |  |  | 2 |  |  | Enhanced production capacity of SMEs |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | BAC |  |  | DPCU |  |  |  |  |  |  |
|  |  | Organize 4No. capacity building training for exporters and potential exporters |  |  |  | District Wide |  |  | 2 |  |  | Enhanced capacity of local exporters |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | BAC |  |  | DPCU |  |  |  |  |  |  |
|  |  | Supply start-up kits to SMEs |  |  |  | District Wide |  |  | √ |  |  | Increased private sector productivity |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 12,000.00 |  |  |  |  |  |  |  |  |  |  | BAC |  |  | DPCU |  |  |  |  |  |  |
|  |  | Facilitate the implementation of the “One District, One Factory programme |  |  |  | District Wide |  |  | - |  |  | Increased job avenues |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | BAC |  |  |  |  |  |  |
|  |  | Facilitate the extension of electricity to all parts of the District to promote development of businesses |  |  |  | District Wide |  |  | √ |  |  | Increased access to power for production |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 80,000.00 |  |  |  |  |  |  |  |  |  |  | ECG |  |  | KADA |  |  |  |  |  |  |
|  |  | Identification of tourism potentials in the District |  |  |  | District Wide |  |  | - |  |  | Increased IGF capacity of the Assembly |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  | community |  |  |  |  |  |  |
| Agricultural Services and Management |  | Partner the private sector to establish a farm machinery mechanization centre |  |  |  | District Wide |  |  | √ |  |  | Increased agricultural productivity |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. Of Agric |  |  | KADA |  |  |  |  |  |  |
|  |  | Organize 4No. training programmes for staff and farmers on rice and maize production |  |  |  | District Wide |  |  | 2 |  |  | Increased agricultural productivity |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. Of Agric |  |  | KADA |  |  |  |  |  |  |
|  |  | Organize 4No. training programmes for staff and farmers on soil fertility management and fertilizer use |  |  |  | District Wide |  |  | 2 |  |  | Increased agricultural productivity |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | - |  |  |  |  |  |  |  |  |  |  | Dept. Of Agric |  |  | KADA |  |  |  |  |  |  |
|  |  | Train Extension, veterinary staff and Livestock farmers in the prevention of scheduled livestock and local poultry diseases |  |  |  | District Wide |  |  | √ |  |  | Increased livestock productivity |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | Vert. Services |  |  |  |  |  |  |
|  |  | Organize 4No. training programmes for staff and farmers on farm planning and budget |  |  |  | District Wide |  |  | 2 |  |  | Increased productivity |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | KADA |  |  |  |  |  |  |
|  |  | Facilitate public education on zoonotic diseases and carry out disease surveillance programmes |  |  |  | District Wide |  |  | - |  |  | Minimise incidence of zoonotic diseases |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | Vert. Services |  |  |  |  |  |  |
|  |  | Organize 4No. training programmes for staff and farmers on principle of crops and livestock production |  |  |  | District Wide |  |  | 2 |  |  | Increased crops and livestock production |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | - |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | Vert. Services |  |  |  |  |  |  |
|  |  | Create and develop land banks for agricultural activities |  |  |  | District Wide |  |  | - |  |  | Availability of land for agricultural use |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  |  |  |  |  |  |  |  | 10,000.00 |  |  |  | Dept. of Agric |  |  | Communities |  |  |  |  |  |  |
|  |  | Develop and disseminate climate smart agricultural activities to farmers |  |  |  | District Wide |  |  | √ |  |  | Climate change impact mitigated |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | ISDs |  |  |  |  |  |  |
|  |  | Facilitate the construction of 2No. irrigation infrastructure |  |  |  | Menusu and Dodo Tamale |  |  | √ |  |  | Increased irrigation farming |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | Private sector/ GOG |  |  |  |  |  |  |
|  |  | Train farmers and staff on storage of cereals |  |  |  | District Wide |  |  | √ |  |  | Reduced post-harvest loses |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | Farmers |  |  |  |  |  |  |
|  |  | Introduce improved planting materials to farmers |  |  |  | District Wide |  |  | √ |  |  | Increased yield |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | CIDA |  |  |  |  |  |  |
|  |  | Support the production of selected crops for domestic and industrial purposes.e.g rice, maize, cassava, ginger etc |  |  |  | District Wide |  |  | √ |  |  | Increased in food crop production |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | KADA/ CIDA |  |  |  |  |  |  |
|  |  | Facilitate the supply of fertilizers to farmers |  |  |  | District Wide |  |  | √ |  |  | Increased crop yield |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | GOG |  |  |  |  |  |  |
|  |  | Vaccinate local poultry and small ruminants against schedule diseases |  |  |  | District Wide |  |  | √ |  |  | Poultry production improved |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | Farmers/ Input dealers |  |  |  |  |  |  |
|  |  | Intensify the use of radio and information van for knowledge dissemination |  |  |  | District Wide |  |  | 12 |  |  | Increased access to agriculture information |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | ISD |  |  |  |  |  |  |
|  |  | Embark on field and home visits by Technical Staff |  |  |  | District Wide |  |  | 13 |  |  | Increased access to agriculture information |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 15,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | Assembly members |  |  |  |  |  |  |
|  |  | Carry out anti-rabies campaign |  |  |  | District Wide |  |  | √ |  |  | Minimise incidence of rabies |  |  | √ |  |  | √ | √ |  |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | Dept. of Agric |  |  | FBOs |  |  |  |  |  |  |
| GOAL 2: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme 2: Social Services Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programmes |  | Activities (Operations) |  |  | Location |  |  |  | Baseline |  |  | Output Indicators |  | Quarterly Time schedule |  |  |  |  |  |  |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st |  |  | 2nd |  |  |  |  | 3rd |  |  | 4th |  |  | GoG |  |  | IGF |  |  |  | DONOR |  |  |  | Lead |  |  |  |  | collaborating |  |  |
| Education, Youth& sports and library service |  | Construction 2No. 3 unit classroom blocks office and store |  |  | District Wide |  |  |  | 4 |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 128,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GetFund |  |  |
|  |  | Complete the on-going construction 1No. 6 unit classroom blocks office and store |  |  | Kosamba |  |  |  | 2 |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 213,427.06 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GetFund |  |  |
|  |  | Construct 1No. Dormitory for GM-JHS |  |  | Kadjebi |  |  |  | - |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 200,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GetFund |  |  |
|  |  | Renovate 2No. 6 unit classroom blocks |  |  | District Wide |  |  |  | 1 |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 40,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GetFund |  |  |
|  |  | Renovate 2No. 3 unit classroom blocks |  |  | District Wide |  |  |  | 2 |  |  | Increased access to education |  |  |  |  | √ |  |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GetFund |  |  |
|  |  | Construct 1No. 3 unit classrooms blocks, office store, ICT and urinal for Model school JHS |  |  | Asato |  |  |  | - |  |  | Improved educational quality |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 300,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GetFund |  |  |
|  |  | Support for self-help/counterpart funding projects |  |  | District Wide |  |  |  | 2 |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 83,786.10 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | Community/Donor |  |  |
|  |  | Support school sports and cultural activities |  |  | District Wide |  |  |  | 4 |  |  | Improved recreation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | World Vision |  |  |
|  |  | Organize annual my First Day at School programmes |  |  | District Wide |  |  |  | 1 |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GES |  |  |
|  |  | Support annual STME clinics |  |  | District Wide |  |  |  | 30 |  |  | Improved capacity |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 12,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GES |  |  |
|  |  | Renovate 2No. Bungalow of the Education staffs |  |  | District Wide |  |  |  | 1 |  |  | Improved housing and welfare |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 40,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GES |  |  |
|  |  | Provide material support(uniforms/shoes) to needy but brilliant students, especially Girls |  |  | District Wide |  |  |  | 300 |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 15,000.00 |  |  |  |  |  |  |  |  |  |  | MP |  |  |  |  | KADA |  |  |
|  |  | Provide financial support to needy but brilliant students, especially Girls |  |  | District Wide |  |  |  | 12 |  |  | Increased access to education |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 15,000.00 |  |  |  |  |  |  |  |  |  |  | MP |  |  |  |  | KADA |  |  |
|  |  | Facilitate career guidance in schools |  |  | District Wide |  |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  |  | 5,000.00 |  |  |  |  |  |  |  | GES |  |  |  |  | World Vision |  |  |
|  |  | Establish and ensure the proper functioning of SMCs and PTAs in all schools |  |  | District Wide |  |  |  | √ |  |  | Improved performance |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  |  | 10,000.00 |  |  |  |  |  |  |  | GES |  |  |  |  | KADA |  |  |
|  |  | Intensify supervision and monitoring of Teaching and Learning activities at all levels |  |  | District Wide |  |  |  | √ |  |  | Improved performance |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | KADA |  |  |
|  |  | Organize School Performance Appraisal meetings in the school communities (SPAM) |  |  | District Wide |  |  |  | √ |  |  | Improved performance |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | KADA |  |  |
|  |  | Monitor BECE and WASSCE and organise annual mock examinations |  |  | District Wide |  |  |  | √ |  |  | Improved BECE/ WASCE performance |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | KADA |  |  |
|  |  | Intensify school health and hygiene education activities in schools |  |  | District Wide |  |  |  | √ |  |  | Improved sanitation, health and hygiene |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | KADA/WV |  |  |
|  |  | Organize capacity training for head teachers and teachers |  |  | District Wide |  |  |  | √ |  |  | Improved capacity |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | KADA |  |  |
|  |  | Promote the construction of WASH facilities in schools |  |  | District Wide |  |  |  | 4 |  |  | Improvement in sanitation and hygiene |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GES/WV |  |  |
|  |  | Institute annual teachers award scheme. |  |  | District Wide |  |  |  | √ |  |  | Enhanced quality of teaching and learning |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | KADA |  |  |
|  |  | Organize capacity training for staff of the education directorate |  |  | Kadjebi |  |  |  | √ |  |  | Enhanced quality of teaching and learning |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | KADA |  |  |
|  |  | Provide financial assistance to students studying science; technical, vocational programmes |  |  | District Wide |  |  |  | √ |  |  | Increased employment avenues |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | GES |  |  |  |  | BAC |  |  |
|  |  | Provision of furniture to schools |  |  | District Wide |  |  |  | 400 |  |  | Enhanced quality of teaching and learning |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GES |  |  |
|  |  | Support development and renovation of sport/ recreational facilities |  |  | District Wide |  |  |  | - |  |  | Improved sports facilities |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | community |  |  |
| Safe and disciplined society |  | Support security agencies to deliver services |  |  | Safe and disciplined society |  |  |  | √ |  |  | Improved security |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | GPS |  |  |  |  | KADA |  |  |
|  |  | Support the effective resolution of chieftaincy disputes |  |  | District Wide |  |  |  | √ |  |  | Chieftaincy roles enhanced in the governance process |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | DISEC |  |  |  |  | DPCU |  |  |
|  |  | Procure and supply Magistrate court with computer set and other office equipment’s |  |  | Kadjebi |  |  |  | - |  |  | Improved security |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | Magistrate court |  |  |
|  |  | Rehabilitate 5No. Police post |  |  | District Wide |  |  |  | - |  |  | Improved security |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  |  |  |  |  |  |  |  |  |  | GPS |  |  |  |  | KADA |  |  |
|  |  | Promote the engagement of youth in planting for food and jobs programme |  |  | District Wide |  |  |  | √ |  |  | Increased employment avenues |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  |  |  |  |  |  |  |  |  |  | Agric Depart. |  |  |  |  | KADA |  |  |
| Public Health Services |  | Construct 4No.CHPS Compound |  |  | Dzindziso Menuso Goldsmith and Dodi Akum |  |  |  | 4 |  |  | Increased access to health services |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 133,540.92 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | Health Depart/Systems for Health |  |  |
|  |  | Renovate and expand infrastructure in 2No. existing Health Centers |  |  | Ahamansu and Dodo Amanfrom |  |  |  | - |  |  | Increased access to health services |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 300,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | Health Depart |  |  |
|  |  | Rehabilitate Health residential buildings |  |  | District Wide |  |  |  | - |  |  | Improved health care delivery |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | Health Depart |  |  |
|  |  | Upgrade Kadjebi Health Centre to a Hospital |  |  | Kadjebi |  |  |  | √ |  |  | Increased access to health services |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 500,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | Health Depart |  |  |
|  |  | Support routine immunizations programmes e.g Polio |  |  | District Wide |  |  |  | √ |  |  | Healthy societies |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  |  | KADA |  |  |
|  |  | Support Malaria control programme |  |  | District Wide |  |  |  | √ |  |  | Healthy societies |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  |  | KADA |  |  |
|  |  | Support mental health promotion activities |  |  | District Wide |  |  |  | √ |  |  | Improved health care delivery |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  |  | KADA |  |  |
|  |  | Undertake HIV/AIDS activities and advocacy programmes with stakeholders |  |  | District Wide |  |  |  | √ |  |  | Reduction in HIV infections |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  |  | KADA |  |  |
|  |  | Organize 2No. Stigma reduction activities |  |  | District Wide |  |  |  | √ |  |  | Reduction in HIV infections |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  |  | KADA |  |  |
|  |  | Undertake Prevention of mother-to-child transmission of HIV activities |  |  | District Wide |  |  |  | √ |  |  | Reduction in HIV infections |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  |  | KADA |  |  |
|  |  | Undertake 2No food safety, nutrition education for the public and screening of food handlers |  |  | District Wide |  |  |  | √ |  |  | Improved Food safety |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | Health Depart |  |  |  |  | KADA/EHSD |  |  |
| Social Welfare and Community Development |  | Undertake skills training in entrepreneurship and offer financial support to PWDs |  |  | District Wide |  |  |  | √ |  |  | Increased access to job opportunities for PWDs |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | Committee of PWDs |  |  |
|  |  | Identify and train 20 persons in sign language interpretation |  |  | District Wide |  |  |  | - |  |  | Effective communication assured |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | Committee of PWDs |  |  |
|  |  | Organize 2No advocacy programmes for PWDs |  |  | District Wide |  |  |  | 2 |  |  | Enhanced capacity of PWDs |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | Committee of PWDs |  |  |
|  |  | Carry out family welfare and child rights protection and promotion services |  |  | District Wide |  |  |  | √ |  |  | Child protection systems strengthened |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | Committee of PWDs |  |  |
|  |  | Support referral case management system |  |  | District Wide |  |  |  | - |  |  | Child protection systems strengthened |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | DCPC |  |  |  |  | SW/CD |  |  |
|  |  | Supervise Day Care centres in the District. |  |  | District Wide |  |  |  | √ |  |  | Child rights protected |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | Committee of PWDs/KADA |  |  |
|  |  | Collaborate with law enforcement agencies to intensify the fight against worst form of child labour, negative practices, child abuse and trafficking |  |  | District Wide |  |  |  | √ |  |  | Rights of children protected |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | Law enforcement agencies |  |  |
|  |  | Offer financial support to brilliant but needy and vulnerable children in schools |  |  | District Wide |  |  |  | √ |  |  | Reduction in poverty |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | GES |  |  |
|  |  | Support the expansion of LEAP to cover more persons in the District |  |  | District Wide |  |  |  | √ |  |  | Reduction in poverty |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | DPCU |  |  |
|  |  | Mainstream gender issues into the development process of the District |  |  | District Wide |  |  |  | √ |  |  | Gender mainstreamed |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | SW/CD |  |  |  |  | DPCU |  |  |
| Environmental Health and Sanitation Services |  | Promote the construction of 200No. household latrines |  |  | District Wide |  |  |  | 126 |  |  | Improved access to sanitation facilities |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | EHSU |  |  |  |  | UNICEF/WV |  |  |
|  |  | Promote the construction of 4No. institutional latrines in schools |  |  |  |  |  |  | 4 |  |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 300,000.00 |  |  |  |  |  |  |  |  |  |  | EHSU |  |  |  |  | UNICEF/WV |  |  |
|  |  | Promote the franchise of 8No. public latrines in the District |  |  |  |  |  |  | 3 |  |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  | EHSU |  |  |  |  | DPCU |  |  |
|  |  | Promote sanitation marketing activities |  |  | District Wide |  |  |  | √ |  |  | Increased access to household sanitation facilities |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | EHSU |  |  |  |  | UNICE |  |  |
|  |  | Promote the construction of 200No. household water treatment and safe storage facilities |  |  | District Wide |  |  |  | 126 |  |  | Sanitized communities |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  | EHSU |  |  |  |  | UNICEF/WV |  |  |
|  |  | Promote the construction of 200No. hand washing with soap facilities |  |  | District Wide |  |  |  | 126 |  |  | Improved sanitation and hygiene |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  |  |  |  |  |  | 20,000.00 |  |  |  | EHSU |  |  |  |  | UNICEF/WV |  |  |
|  |  | Review, update and implement the DESSAP |  |  | District Wide |  |  |  | √ |  |  | Sanitized communities |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  | 20,000.00 |  |  |  | EHSU |  |  |  |  | UNICEF/WV |  |  |
|  |  | Undertake effective liquid and solid waste management activities |  |  | District Wide |  |  |  | √ |  |  | Improved solid and liquid waste management system |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  | 30,000.00 |  |  |  | EHSU |  |  |  |  | UNICEF/WV |  |  |
|  |  | Organize award scheme for ODF communities |  |  | District Wide |  |  |  | - |  |  | Sanitized communities |  |  |  |  |  |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  | 20,000.00 |  |  |  | EHSU |  |  |  |  | UNICEF/WV/KADA |  |  |
|  |  | Maintain the running cost of sanitation and other official vehicles |  |  | District Wide |  |  |  | √ |  |  | Improved efficiency of vehicles |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | EHSU |  |  |  |  | KADA |  |  |
|  |  | Organize 12No. Monthly National Sanitation Days |  |  | District Wide |  |  |  | 4 |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 12,000.00 |  |  |  |  |  |  |  |  |  |  | EHSU |  |  |  |  | KADA |  |  |
|  |  | Distribute waste bins to residents in the District |  |  | District Wide |  |  |  | 34 |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | zoomlion |  |  |  |  | EHSU |  |  |
|  |  | Undertake disinfestation and fumigation activities |  |  | District Wide |  |  |  | √ |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 200,000.00 |  |  |  |  |  |  |  |  |  |  | zoomlion |  |  |  |  | EHSU |  |  |
|  |  | Renovate 1No. refuse skip truck |  |  | District Wide |  |  |  | - |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | EHSU |  |  |
|  |  | Renovate 15No. refuse containers |  |  | District Wide |  |  |  | - |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | EHSU |  |  |
|  |  | Procure sanitary tools and equipment |  |  | Kadjebi |  |  |  | √ |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | EHSU |  |  |
|  |  | Complete acquisition of final disposal site |  |  | Kadjebi |  |  |  | √ |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  |  |  | EHSU |  |  |
|  |  | Maintenance of final disposal site |  |  | Kadjebi |  |  |  | √ |  |  | Improved environmental sanitation |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  |  | 200,000.00 |  |  |  |  |  |  |  |  |  |  | zoomlion |  |  |  |  | EHSU/KADA |  |  |
| GOAL 3: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Programme 3: Infrastructure Development and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sub-programmes |  | Activities (Operations) |  |  |  | Location |  | Baseline |  |  | Output Indicators |  |  |  | Quarterly Time schedule |  |  |  |  |  |  |  |  |  |  |  |  | Indicative Budget |  |  |  |  |  |  |  |  |  |  |  | Implementing Agencies |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1st |  |  | 2nd |  |  |  |  | 3rd |  |  | 4th |  | GoG |  |  |  | IGF |  |  |  | DONOR |  |  |  | Lead |  |  | collaborating |  |  |  |  |
| Infrastructure Development and Management/ Urban Roads and Transport Services |  | Reshaping of 30km feeder roads |  |  |  | District Wide |  | 18 |  |  | Improved transportation systems |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | Urban Roads/ Ghana Highways Authority |  |  |  |  |
|  |  | Spot improvement of 30km feeder roads |  |  |  | Amanfrom-Dapaa Jn. |  | - |  |  | Improved transportation systems |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 50,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | Urban Roads/ Ghana Highways Authority |  |  |  |  |
|  |  | Construction of 2no. foot bridges |  |  |  | District Wide |  | 1 |  |  | Foot bridges constructed |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | MWD |  |  | MPCU |  |  |  |  |
|  |  | Construct of 1No. drains |  |  |  | District Wide |  | 3 |  |  | Improve drainage |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | EHSU |  |  |  |  |
|  |  | Construction of speed ramps in the District |  |  |  | District Wide |  | - |  |  | Safe transportation systems |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | Urban Roads/ Ghana Highways Authority |  |  |  |  |
|  |  | Construction of Fire/Ambulance Bay |  |  |  | Kadjebi |  | - |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 235,425.00 |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | DWD |  |  |  |  |
|  |  | Asphalting of Kadjebi Township roads |  |  |  | Kadjebi |  | - |  |  | Improved transportation systems |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 1,000,000.00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Spatial Planning |  | Undertake regular site inspection of development activities |  |  |  | District Wide |  | √ |  |  | Well planned communities |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | PPD |  |  | DWD |  |  |  |  |
|  |  | Enforce by-laws on physical developments |  |  |  | District Wide |  | √ |  |  | Well planned communities |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | PPD |  |  | DWD |  |  |  |  |
|  |  | Acquire land for establishment of cemetery at Kadjebi |  |  |  | Kadjebi |  | - |  |  | Well planned communities |  |  |  | √ |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  |  | EHSU |  |  | PPD |  |  |  |  |
|  |  | Acquire land for establishment of New Lorry Station at Kadjebi |  |  |  | Kadjebi |  | - |  |  | Well planned communities |  |  |  | √ |  |  |  |  |  |  |  |  |  |  |  |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | PPD |  |  |  |  |
|  |  | Undertake capacity building programmes for Physical Planning Department officers |  |  |  | Kadjebi |  | √ |  |  | Enhanced capacity of PPD officers |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | PPD |  |  | HR Unit |  |  |  |  |
|  |  | Undertake public sensitization programmes on Physical development |  |  |  | District Wide |  | √ |  |  | Well planned communities |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | PPD |  |  | ISD |  |  |  |  |
|  |  | Prepare structure and site plans for selected communities |  |  |  | District Wide |  | - |  |  | Well planned communities |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | PPD |  |  | DWD/EHSU |  |  |  |  |
|  |  | Ensure proper acquisition, documentation and payment for government/ KADA acquired lands |  |  |  | District Wide |  | - |  |  | Secured government lands |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | PPD |  |  | DWD/EHSU |  |  |  |  |
|  |  | Provide and maintain street lights in the District |  |  |  | District Wide |  | √ |  |  | Well secured communities |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | Assembly men |  |  |  |  |
|  |  | Continue Street naming and property addressing system |  |  |  | District Wide |  | √ |  |  | Well planned communities |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 50,000.00 |  |  |  |  |  |  |  |  |  |  |  | PPD |  |  | DWD |  |  |  |  |
| Public Works, Rural Housing and Water Management |  | Promote and construct 2No. pipe schemes in the District |  |  |  | Dodo Amanfrom, Poase cement |  | - |  |  | Improved access to potable water |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 500,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DWST |  |  |  |  |
|  |  | Promote and construct 13No. boreholes in the District |  |  |  | District Wide |  | 12 |  |  | Improved access to potable water |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 35,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DWST |  |  |  |  |
|  |  | Rehabilitate 2No. piped schemes in the District |  |  |  | Ahamansu, Mempeasem |  | - |  |  | Improved access to potable water |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DWST |  |  |  |  |
|  |  | Rehabilitate 20No. boreholes in the District |  |  |  | District Wide |  | 15 |  |  | Improved access to potable water |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DWST |  |  |  |  |
|  |  | Review, gazette and enforce KADAs bye-laws on sanitation |  |  |  | District Wide |  | √ |  |  | Improved sanitation |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | EHSU |  |  |  |  |
|  |  | Advertise the District Water and Sanitation Plan (DWSP) |  |  |  | Nation Wide |  | - |  |  | Improved access to potable water |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DWST |  |  |  |  |
|  |  | Organize capacity programmes for actors in Water management |  |  |  | District Wide |  | √ |  |  | Improved access to potable water |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | HR/DWST |  |  |  |  |
|  |  | Embark on regular monitoring of Water facility on quality, effective management and reporting mechanisms |  |  |  | District Wide |  | √ |  |  | Improved access to potable water |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DWST |  |  |  |  |
| Improve the welfare and infrastructure for staff |  | Prepare and implement operation and maintenance plan for the Assembly |  |  |  | District Wide |  | √ |  |  | Assembly properties maintained |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | DPCU |  |  |  |  |
|  |  | Renovate 4No Assembly staff bungalows |  |  |  | Kadjebi |  | 3 |  |  | Enhanced staff welfare |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 40,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DPCU |  |  |  |  |
|  |  | Rehabilitation of DCE residency Building |  |  |  | Kadjebi |  |  |  |  | Enhanced staff welfare |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 300,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DPCU |  |  |  |  |
|  |  | Fencing of DCDs Bungalow |  |  |  | Kadjebi |  |  |  |  | Enhanced staff welfare |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 80,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DPCU |  |  |  |  |
|  |  | Construction of staff villa |  |  |  | Kadjebi |  |  |  |  | Enhanced staff welfare |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 200,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DPCU |  |  |  |  |
|  |  | Construct 5No. Area council facilities |  |  |  | Dodi, Dodo, Asato, Kadjebi and Amanta |  |  |  |  | Improved popular participation |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 500,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DPCU |  |  |  |  |
|  |  | Rehabilitate 1No. Area Council facility |  |  |  | Ahamansu |  |  |  |  | Enhanced productivity |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 100,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DPCU |  |  |  |  |
|  |  | Renovate Assembly block, Assembly Hall and other Offices of departments |  |  |  | Kadjebi |  |  |  |  | Assembly properties maintained |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 30,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWD |  |  | DPCU |  |  |  |  |
|  |  | Procure 1No. Power Generating Plant |  |  |  | Kadjebi |  |  |  |  | Enhanced productivity |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 50,000.00 |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | DPCU |  |  |  |  |
| Environmental Management/ Natural Resource Conservation and Management |  | Organize sensitization programmes on water resources protection |  |  |  | District Wide |  |  |  |  | Water resources protected |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | DWST |  |  | DPCU |  |  |  |  |
|  |  | Support afforestation programmes along river basins |  |  |  | District Wide |  |  |  |  | Water resources protected |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | NADMO |  |  | YEA/NFS/EHSD/MoFA |  |  |  |  |
|  |  | Facilitate Nursing and supply of Teak Tree seedlings to schools and communities |  |  |  | District Wide |  |  |  |  | Afforestation |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | NADMO |  |  | YEA/NFS/EHSD/MoFA |  |  |  |  |
|  |  | Organize 2No. Public sensitization programmes on conservation of wildlife resources and protection of biodiversity |  |  |  | District Wide |  |  |  |  | Wildlife resources conserved |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | NADMO |  |  | YEA/NFS/EHSD/MoFA |  |  |  |  |
| Disaster Prevention and Management |  | Undertake 2No capacity building programmes on climate change mitigation and adaptation |  |  |  | District Wide |  |  |  |  | Climate change impacts mitigated |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 10,000.00 |  |  |  |  |  |  |  |  |  |  |  | NADMO |  |  | YEA/NFS/EHSD/MoFA |  |  |  |  |
|  |  | Sensitize the public on disaster risk management and early warning systems |  |  |  | District Wide |  |  |  |  | Climate change impacts mitigated |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 5,000.00 |  |  |  |  |  |  |  |  |  |  |  | NADMO |  |  | YEA/NFS/EHSD/MoFA |  |  |  |  |
|  |  | Supply relief items to disaster victims |  |  |  | District Wide |  |  |  |  | Reduced disaster impact |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | NADMO |  |  | KADA |  |  |  |  |
| GOAL 5: ROLE IN INTERNATIONAL AFFAIRS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| General Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration |  | Support linkages between Ambassadors, High Commissioners, foreign donors, investors and DCE to maximize investment and trade opportunities. |  |  |  | Kadjebi |  | - |  |  | No. of investment and trade opportunities created for the Assembly |  |  |  | √ |  |  | √ |  |  |  |  | √ |  |  | √ |  | 20,000.00 |  |  |  |  |  |  |  |  |  |  |  | KADA |  |  | Trade Ministry |  |  |  |  |